## Technical Document
1. Project Scope (Technical Document Style) 1.1 Purpose The project aims to design, develop, build, and operate a fully integrated “Ranch Management System” consisting of a high‑spec main residence, agricultural outbuildings, self‑sustainability subsystems, land infrastructure, energy systems, and in‑service operational capabilities. The objective is to deliver a complete lifestyle environment with autonomous or semi‑autonomous capabilities for energy, water, food production, and property management. 1.2 In‑Scope The project includes the following components, treated as system modules: Residential System Main house (5 bedrooms, en‑suites, entertainment basement, etc.) Outdoor kitchen, orangery, sunroom Wood‑fire heating module Fit‑out subsystems (kitchens, bathrooms, utilities) Outbuilding System Two annex/cottage units Garage module Gym facility (sauna, cold plunge, studios, hydro pool) Barn structures Greenhouse & polytunnel Energy & Sustainability System Solar generation subsystem Battery storage subsystem Wind turbine subsystem Water collection & filtration subsystem Borehole for agricultural water Septic & waste management subsystem Land & Environmental System Driveway (500m) Fencing, feeding areas, irrigation network Wild pond and landscaping Livestock housing & care modules Operational & Support System Staff model (domestic & agricultural) Utilities model (energy, water, waste) Maintenance & obsolescence model Feed and livestock cost tracking system Project Phasing Phase 1: Planning and coordination Phase 2: Design, manufacture, procurement Phase 3: Build execution Phase 4: Testing, acceptance, certification Phase 5: In‑service operations 1.3 Out‑of‑Scope Land acquisition (assumed already owned) Budget constraints (no cap defined) Monetisation of agricultural output Offsite accommodation for workers Non-essential luxury expansions not listed in requirements (e.g. helipad, tennis courts, etc.) 2. Functional Requirements (FR) Written like software feature requirements, using “The system shall…” 2.1 Residential System Requirements FR‑01: The system shall provide a main residence with 5 double en‑suite bedrooms, including 2 with dressing rooms. FR‑02: The system shall provide a high‑spec kitchen and separate walk‑in pantry. FR‑03: The system shall provide a walk‑in utility room with storage functions. FR‑04: The basement shall include a wine cellar, entertainment area, bar, and pool table area. FR‑05: The system shall include 2 offices and a library. FR‑06: The system shall support indoor/outdoor integrated living via an orangery and sun room. FR‑07: The system shall include 2 downstairs guest toilets. 2.2 Outbuilding System Requirements FR‑20: The system shall include 2 annex units operating as standalone accommodation modules. FR‑21: The system shall include a multi‑vehicle garage. FR‑22: The system shall include a gym module containing: Sauna Bike studio Yoga studio Weight area Cold plunge Hydro pool FR‑23: The system shall include barns for smallholding operations. 2.3 Sustainability & Utilities Requirements FR‑40: The system shall generate renewable electricity via solar panels. FR‑41: The system shall store power using battery packs. FR‑42: The system shall generate supplementary energy from wind turbines. FR‑43: The system shall support water capture and filtration for usage across buildings. FR‑44: The farm area shall be supplied by a borehole. FR‑45: The main house shall connect to mains water. FR‑46: The system shall manage sewage via a septic tank. FR‑47: The system shall include a full-site irrigation network supplying animal troughs. 2.4 Land & Environmental Requirements FR‑60: The system shall provide ~2 acres of garden and landscaped outdoor areas. FR‑61: The system shall provide a 500m paved driveway. FR‑62: The system shall include a pond supporting wildlife. FR‑63: The system shall include fencing and animal feeding areas. FR‑64: The system shall include growing environments (greenhouse, polytunnel, veg patches, fruit trees). 2.5 Smallholding & Livestock Requirements FR‑80: The system shall support smallholding livestock including: Runner ducks Chickens Llamas Highland cows Quails FR‑81: The system shall support feed storage, delivery, and safe animal housing. 2.6 Project Management & Delivery Requirements FR‑100: The project shall include a project manager, surveyors, architects, and labour resources. FR‑101: The system shall implement phased delivery (planning → design → build → testing → in‑service). FR‑102: Major purchases shall require a 20% deposit 6 months before delivery. FR‑103: Medium purchases shall require a 10% deposit 3 months before delivery. 2.7 In‑Service Operational Requirements FR‑120: The system shall include domestic staff for ongoing cleaning and maintenance. FR‑121: The system shall include farmhands for livestock and land operations. FR‑122: The system shall capture data on ongoing utility usage, septic cycles, feed consumption, and maintenance. 3. Non‑Functional Requirements (NFR) Even though this is a physical build, the NFR model from software translates well. 3.1 Reliability NFR‑01: Energy systems shall provide year‑round operation with >90% uptime excluding weather‑related downtime. NFR‑02: Water supply (borehole + mains) shall operate with redundancy. 3.2 Maintainability NFR‑10: All systems shall be designed for routine maintenance & annual serviceability. NFR‑11: All materials shall be selected with >15‑year durability where feasible. 3.3 Scalability NFR‑20: The site design shall allow expansion of: Additional livestock More energy storage Additional agricultural structures 3.4 Usability NFR‑30: Residential, agricultural, and sustainability systems shall be operable by non‑technical users. 3.5 Security NFR‑40: The site shall support rural physical security including fencing and access control. 3.6 Performance NFR‑50: Energy generation systems shall contribute to lowering grid draw by >60% annually. NFR‑51: Irrigation systems must support continuous water delivery to livestock. 4. Assumptions (Technical Format) A‑01: The land is already owned and requires no acquisition process. A‑02: Exact acreage of land, garden, smallholding areas will be determined during detailed design. A‑03: All listed buildings and components are mandatory baseline scope. A‑04: The build will occur in rural North Devon with risk of transportation and supply delays. A‑05: The owner has no financial constraints; cost is for analysis only. A‑06: Deposits: Major item deposit = 20%, 6 months pre‑manufacture/delivery Medium item deposit = 10%, 3 months pre‑delivery A‑07: Grid power connection is technically feasible at the site location. A‑08: Weather may affect build timelines and logistics. A‑09: UK planning permission will be granted without exceptional conditions. A‑10: All livestock are permitted under local agricultural regulations.

## Cost Lines (hidden)
CBS_Code | CBS_Description | CBS_Level | WBS_Phase | Unit | Qty_Estimate | Size_Assumption | Unit_Cost_Low_GBP | Unit_Cost_ML_GBP | Unit_Cost_High_GBP | Total_Low_GBP | Total_ML_GBP | Total_High_GBP | Duration_Low_days | Duration_ML_days | Duration_High_days | Notes_Assumptions
C1.1.1 | Planning & Project Management | 3 | Phase 1 | Months | 18 | 18 month pre-build programme | 4000 | 7000 | 11000 | 72000 | 126000 | 198000 | 90 | 150 | 240 | PM, planning consultant, architect prelims, coordination
C1.1.2 | Surveys Site Investigations & Permits | 3 | Phase 1-2 | Item | 1 | Topographic, geo, ecology, planning app | 35000 | 60000 | 95000 | 35000 | 60000 | 95000 | 30 | 60 | 90 | Topo survey, ground investigation, ecology, planning application fees
C1.2.1 | Main House | 3 | Phase 3 | Sum | 1 | 800m² GIA assumed |  |  |  | 1800000 | 2800000 | 4200000 | 300 | 450 | 600 | Modern traditional farmhouse, high spec
C1.2.2 | Annexes x2 | 3 | Phase 3 | Sum | 2 | 120m² each bungalow style |  |  |  | 240000 | 380000 | 580000 | 120 | 180 | 240 | Two country cottage style annexes
C1.2.3 | Garage | 3 | Phase 3 | Sum | 1 | 200m² large detached |  |  |  | 80000 | 140000 | 220000 | 60 | 90 | 120 | Large detached garage block
C1.2.4 | Barns & Outbuildings | 3 | Phase 3 | Sum | 1 | 400m² total barn footprint |  |  |  | 180000 | 280000 | 420000 | 90 | 120 | 180 | Agricultural barns, smallholding structures
C1.2.5 | Farm Infrastructure & Smallholding | 3 | Phase 3 | Sum | 1 | ~15 acres farmland |  |  |  | 120000 | 200000 | 340000 | 90 | 120 | 180 | Fencing, irrigation, animal housing, growing areas
C1.2.6 | Utilities & Infrastructure | 3 | Phase 2-3 | Sum | 1 | Rural connection, septic, borehole |  |  |  | 220000 | 380000 | 580000 | 60 | 90 | 120 | Grid, septic, borehole, drainage, site services
C1.2.7 | Outdoor & Landscaping | 3 | Phase 3 | Sum | 1 | ~4 acres garden + pond + paths |  |  |  | 180000 | 320000 | 520000 | 60 | 90 | 120 | Formal garden, wild pond, furniture, lighting
C1.2.1.1 | Substructure | 4 | Phase 3 | m² | 800 | 800m² strip/raft foundations | 180 | 260 | 400 | 144000 | 208000 | 320000 | 30 | 45 | 70 | Strip or raft foundations, ground beams, DPC, ground floor slab. Rural ground conditions variable.
C1.2.1.2 | Superstructure Walls | 4 | Phase 3 | m² | 800 | External & loadbearing walls, ~800m² GIA | 220 | 320 | 480 | 176000 | 256000 | 384000 | 30 | 50 | 75 | Blockwork/stone clad external, loadbearing internals. Modern trad farmhouse style.
C1.2.1.3 | Roof Structure | 4 | Phase 3 | m² | 900 | Roof plan area ~900m² inc overhangs | 120 | 180 | 280 | 108000 | 162000 | 252000 | 25 | 40 | 60 | Timber roof structure, complex farmhouse pitches, structural engineer input
C1.2.1.4 | External Envelope | 4 | Phase 3 | m² | 900 | Roof covering + external wall finish | 95 | 145 | 220 | 85500 | 130500 | 198000 | 20 | 35 | 55 | Natural slate or clay tile roof, render/stone facade, windows & external doors
C1.2.1.5 | First Fix MEP | 4 | Phase 3 | m² | 800 | 800m² GIA | 75 | 115 | 175 | 60000 | 92000 | 140000 | 20 | 30 | 50 | First fix plumbing, heating pipework, electrical cabling, data/AV cabling
C1.2.1.6 | Internal Walls & Partitions | 4 | Phase 3 | m² | 600 | Estimated 600m² of partition walls | 45 | 70 | 110 | 27000 | 42000 | 66000 | 15 | 25 | 40 | Timber stud and blockwork partitions throughout
C1.2.1.7 | Plaster & Insulation | 4 | Phase 3 | m² | 800 | 800m² GIA | 40 | 60 | 90 | 32000 | 48000 | 72000 | 20 | 30 | 45 | Full insulation package (walls/roof/floor), plastering throughout
C1.2.1.8 | Second Fix & Fixtures | 4 | Phase 3 | m² | 800 | 800m² GIA | 80 | 130 | 200 | 64000 | 104000 | 160000 | 25 | 40 | 60 | Second fix plumbing, electrical fit-out, sanitaryware, radiators/UFH
C1.2.1.9 | Finishes | 4 | Phase 3 | m² | 800 | 800m² GIA | 65 | 110 | 180 | 52000 | 88000 | 144000 | 20 | 35 | 55 | Floor finishes, tiling, decoration, joinery finishes throughout
C1.2.1.10 | Basement & Entertainment | 4 | Phase 3 | m² | 150 | 150m² basement: wine cellar + bar + entertainment | 950 | 1400 | 2200 | 142500 | 210000 | 330000 | 40 | 60 | 90 | Tanked basement, wine cellar racking, bar fitout, AV/entertainment, pool table area
C1.2.1.11 | Kitchen Pantry & Utility | 4 | Phase 3 | Item | 1 | Large farm kitchen + walk-in pantry + utility | 65000 | 110000 | 180000 | 65000 | 110000 | 180000 | 15 | 25 | 40 | Bespoke high-spec kitchen, Aga/range, island, walk-in pantry, utility room
C1.2.1.12 | Library Offices & Lounge | 4 | Phase 3 | Item | 1 | Library, x2 offices, lounge, coffee bar | 35000 | 60000 | 95000 | 35000 | 60000 | 95000 | 15 | 20 | 35 | Bespoke joinery, shelving, fitted desks, fireplace surrounds
C1.2.1.13 | Orangery & Outdoor Kitchen | 4 | Phase 3 | Item | 1 | Garden orangery + outdoor kitchen structure | 55000 | 90000 | 145000 | 55000 | 90000 | 145000 | 20 | 30 | 50 | Hardwood/steel orangery structure, glazing, outdoor kitchen with appliances
C1.2.1.14 | Solar Panels & Wind Turbines | 4 | Phase 3 | Item | 1 | ~30kWp solar + small wind turbine | 35000 | 60000 | 95000 | 35000 | 60000 | 95000 | 10 | 15 | 25 | Roof/ground mounted solar array, battery storage packs, small wind turbine
C1.2.1.15 | Water Collection & Treatment | 4 | Phase 3 | Item | 1 | Rainwater harvesting + UV treatment system | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 7 | 10 | 18 | Rainwater harvesting tanks, filtration, UV treatment, grey water system
C1.2.1.16 | Septic Tank | 4 | Phase 3 | Item | 1 | Large capacity septic/treatment plant | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | Package sewage treatment plant sized for main house. Percolation test required.
C1.2.1.17 | Driveway & Paving | 4 | Phase 3 | m² | 2000 | 500m driveway ~4m wide + courtyard = ~2000m² | 45 | 75 | 120 | 90000 | 150000 | 240000 | 20 | 30 | 45 | Tarmac/gravel driveway, block paving courtyard, excess slabs used in garden
C1.2.1.18 | Garden Landscaping & Hydro Pool | 4 | Phase 3 | Item | 1 | Formal gardens ~2 acres + hydro pool | 80000 | 140000 | 220000 | 80000 | 140000 | 220000 | 30 | 45 | 70 | Landscaping, planting, hard landscaping, hydrotherapy pool installation
C1.2.1.19 | Gym Spa Sauna Cold Plunge Yoga Studio | 4 | Phase 3 | Item | 1 | Detached or attached wellness complex ~150m² | 120000 | 200000 | 320000 | 120000 | 200000 | 320000 | 30 | 45 | 70 | Gym fitout, sauna cabin, cold plunge tank, yoga/bike studio, shower/changing facilities
C1.2.1.1.1 | Site Clearance & Levelling | 5 | Phase 3 | m² | 1200 | 1200m² clearance area | 8 | 14 | 22 | 9600 | 16800 | 26400 | 5 | 8 | 14 | Strip topsoil, level site, remove vegetation
C1.2.1.1.2 | Excavation & Earthworks | 5 | Phase 3 | m³ | 1500 | Est 1500m³ dig incl basement | 28 | 42 | 65 | 42000 | 63000 | 97500 | 8 | 12 | 20 | Bulk excavation, basement dig, spoil removal (rural haulage premium)
C1.2.1.1.3 | Foundation Concrete & Reinforcement | 5 | Phase 3 | m² | 800 | 800m² strip/raft | 85 | 125 | 190 | 68000 | 100000 | 152000 | 10 | 15 | 25 | Concrete foundations, rebar, blinding, formwork
C1.2.1.1.4 | Ground Floor Slab | 5 | Phase 3 | m² | 800 | 800m² insulated slab | 35 | 55 | 80 | 28000 | 44000 | 64000 | 5 | 8 | 14 | Insulated concrete ground floor slab with UFH provision
C1.2.1.1.5 | Damp Proof Course & Tanking | 5 | Phase 3 | m² | 800 | 800m² + basement tanking 600m² | 18 | 28 | 42 | 14400 | 22400 | 33600 | 3 | 5 | 8 | DPC throughout, full basement tanking system
C1.2.1.10.1 | Basement Structural Shell | 5 | Phase 3 | m² | 150 | 150m² tanked basement shell | 350 | 500 | 780 | 52500 | 75000 | 117000 | 15 | 25 | 40 | Structural walls, tanking, slab, waterproofing membrane
C1.2.1.10.2 | Wine Cellar Fitout | 5 | Phase 3 | Item | 1 | ~30m² climate controlled | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | Racking, temperature control, tiling, lighting
C1.2.1.10.3 | Bar Fitout | 5 | Phase 3 | Item | 1 | ~25m² bar area | 15000 | 28000 | 48000 | 15000 | 28000 | 48000 | 5 | 8 | 12 | Bespoke bar cabinetry, sink, refrigeration, bar top, backlit shelving
C1.2.1.10.4 | Entertainment Area | 5 | Phase 3 | Item | 1 | ~60m² pool table, cinema, seating | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 5 | 8 | 12 | AV system, projector/screen, acoustic panels, pool table, seating
C1.2.1.10.5 | Basement MEP | 5 | Phase 3 | Item | 1 | Basement MEP services | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 5 | 8 | 12 | HVAC, lighting, electrical, data, plumbing for basement
C1.2.1.11.1 | Kitchen Units & Cabinetry | 5 | Phase 3 | Item | 1 | Bespoke high spec kitchen ~35m² | 28000 | 55000 | 95000 | 28000 | 55000 | 95000 | 5 | 8 | 14 | Bespoke painted Shaker-style or similar, soft close, integrated
C1.2.1.11.2 | Kitchen Appliances | 5 | Phase 3 | Item | 1 | Full appliance package | 12000 | 22000 | 40000 | 12000 | 22000 | 40000 | 3 | 5 | 8 | Aga or range cooker, integrated fridge-freezer, dishwasher, microwave, wine cooler
C1.2.1.11.3 | Kitchen Worktops & Sink | 5 | Phase 3 | Item | 1 | Stone worktops, butler sink | 5000 | 9000 | 16000 | 5000 | 9000 | 16000 | 2 | 3 | 5 | Quartz or granite worktops, Belfast sink, taps
C1.2.1.11.4 | Pantry Fitout | 5 | Phase 3 | Item | 1 | Walk-in pantry ~12m² | 4500 | 8000 | 14000 | 4500 | 8000 | 14000 | 2 | 3 | 5 | Shelving, worktop, small sink, larder storage
C1.2.1.11.5 | Utility Room Fitout | 5 | Phase 3 | Item | 1 | Walk-in utility ~14m² | 6000 | 10000 | 18000 | 6000 | 10000 | 18000 | 2 | 3 | 5 | Worktops, laundry appliances, sink, storage, boot room
C1.2.1.12.1 | Library Bespoke Joinery | 5 | Phase 3 | Item | 1 | Floor-to-ceiling shelving ~20m² | 12000 | 20000 | 35000 | 12000 | 20000 | 35000 | 5 | 8 | 12 | Bespoke painted shelving, rolling ladder, reading nook
C1.2.1.12.2 | Office Fitout x2 | 5 | Phase 3 | Item | 2 | ~14m² each | 4000 | 7000 | 12000 | 8000 | 14000 | 24000 | 3 | 5 | 8 | Fitted desks, storage, data/AV points, joinery
C1.2.1.12.3 | Lounge Fireplace & Joinery | 5 | Phase 3 | Item | 1 | Feature fireplace + joinery | 8000 | 14000 | 24000 | 8000 | 14000 | 24000 | 3 | 5 | 8 | Log burning stove or open fire, bespoke surround, TV joinery
C1.2.1.12.4 | Coffee Bar Fitout | 5 | Phase 3 | Item | 1 | Coffee bar area ~6m² | 3500 | 6000 | 10000 | 3500 | 6000 | 10000 | 2 | 3 | 5 | Cabinetry, worktop, commercial coffee machine, sink
C1.2.1.12.5 | Sunroom Fitout | 5 | Phase 3 | Item | 1 | Sunroom ~20m² | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 5 | 8 | 12 | Glazed extension or internal sunroom, bifolds/glazed roof, tiling, blinds
C1.2.1.13.1 | Orangery Structure & Glazing | 5 | Phase 3 | m² | 45 | 45m² garden orangery | 800 | 1300 | 2000 | 36000 | 58500 | 90000 | 10 | 18 | 30 | Hardwood or aluminium frame, roof lantern, large glazed panels
C1.2.1.13.2 | Orangery Internal Finishes | 5 | Phase 3 | Item | 1 | Flooring, plastering, doors | 6000 | 10000 | 18000 | 6000 | 10000 | 18000 | 5 | 8 | 12 | Tiled floor, plastered walls, bifold garden doors
C1.2.1.13.3 | Outdoor Kitchen Structure & Cover | 5 | Phase 3 | Item | 1 | Outdoor kitchen ~20m² covered | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | Pergola/roof structure, stone or render walls
C1.2.1.13.4 | Outdoor Kitchen Appliances & Fitout | 5 | Phase 3 | Item | 1 | BBQ, sink, fridge, worktops | 6000 | 12000 | 22000 | 6000 | 12000 | 22000 | 3 | 5 | 8 | Built-in BBQ, outdoor fridge, stone worktops, outdoor sink
C1.2.1.14.1 | Solar PV Panels | 5 | Phase 3 | kWp | 30 | 30kWp array | 900 | 1300 | 1900 | 27000 | 39000 | 57000 | 5 | 8 | 12 | Roof or ground mounted solar PV, inverters, mounting
C1.2.1.14.2 | Battery Storage Packs | 5 | Phase 3 | kWh | 30 | 30kWh storage | 600 | 900 | 1400 | 18000 | 27000 | 42000 | 2 | 3 | 5 | Lithium battery packs, BMS, integration with solar
C1.2.1.14.3 | Small Wind Turbine | 5 | Phase 3 | Item | 1 | ~6kW turbine | 12000 | 20000 | 35000 | 12000 | 20000 | 35000 | 5 | 8 | 14 | Planning permission likely needed, tower, grid tie inverter
C1.2.1.18.1 | Formal Garden Design & Planting | 5 | Phase 3 | m² | 3000 | ~3000m² formal garden | 12 | 22 | 38 | 36000 | 66000 | 114000 | 15 | 25 | 40 | Landscape design, soil prep, planting, turf
C1.2.1.18.2 | Hard Landscaping Paths & Patios | 5 | Phase 3 | m² | 500 | Paths, patios, steps ~500m² | 65 | 110 | 180 | 32500 | 55000 | 90000 | 10 | 15 | 25 | Natural stone or porcelain paving, edging
C1.2.1.18.3 | Hydrotherapy Pool | 5 | Phase 3 | Item | 1 | Outdoor hydro pool ~8x4m | 35000 | 60000 | 100000 | 35000 | 60000 | 100000 | 15 | 20 | 35 | Heated outdoor pool, jets, filtration, cover, surround
C1.2.1.18.4 | Pool Plant Room & Services | 5 | Phase 3 | Item | 1 | Plant room for pool equipment | 5000 | 9000 | 16000 | 5000 | 9000 | 16000 | 3 | 5 | 8 | Pump house, heat pump, electrical, plumbing
C1.2.1.19.1 | Gym Structure & Shell | 5 | Phase 3 | m² | 60 | ~60m² gym area | 350 | 500 | 750 | 21000 | 30000 | 45000 | 10 | 15 | 25 | Structural shell, insulation, floor, windows, doors
C1.2.1.19.2 | Gym Fitout & Equipment | 5 | Phase 3 | Item | 1 | Weight area, cardio, mats | 20000 | 40000 | 70000 | 20000 | 40000 | 70000 | 5 | 8 | 14 | Rubber flooring, squat rack, dumbbells, cardio machines, mirrors
C1.2.1.19.3 | Sauna Cabin | 5 | Phase 3 | Item | 1 | 4-person sauna | 8000 | 14000 | 22000 | 8000 | 14000 | 22000 | 3 | 5 | 8 | Pre-built or bespoke sauna cabin, heater, benching
C1.2.1.19.4 | Cold Plunge Tank | 5 | Phase 3 | Item | 1 | Cold plunge unit | 4000 | 8000 | 15000 | 4000 | 8000 | 15000 | 2 | 3 | 5 | Stainless or timber cold plunge, chiller unit
C1.2.1.19.5 | Yoga & Bike Studio | 5 | Phase 3 | Item | 1 | ~30m² dual purpose studio | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 5 | 8 | 12 | Sprung floor, mirrors, AV/sound, bike fixings, storage
C1.2.1.19.6 | Spa Shower & Changing | 5 | Phase 3 | Item | 1 | Wet room shower, changing area | 8000 | 14000 | 24000 | 8000 | 14000 | 24000 | 3 | 5 | 8 | Tiled wet room, steam option, vanity, lockers
C1.2.2.1 | Substructure & Superstructure | 4 | Phase 3 | m² | 120 | 120m² per annex x2 = 240m² | 220 | 320 | 480 | 52800 | 76800 | 115200 | 25 | 40 | 60 | Foundations, walls, floors per annex
C1.2.2.2 | Roof & Envelope | 4 | Phase 3 | m² | 140 | Roof area ~140m² per unit | 90 | 140 | 210 | 25200 | 39200 | 58800 | 15 | 25 | 40 | Pitched roof, external envelope, windows, doors
C1.2.2.3 | Internal Fitout & Finishes | 4 | Phase 3 | m² | 120 | Full fitout per 120m² unit x2 | 180 | 280 | 420 | 43200 | 67200 | 100800 | 20 | 30 | 50 | Kitchen, bathroom, flooring, decoration, joinery
C1.2.2.4 | MEP Systems | 4 | Phase 3 | m² | 120 | MEP per annex x2 | 65 | 100 | 155 | 15600 | 24000 | 37200 | 10 | 15 | 25 | Heating, plumbing, electrical, data per annex
C1.2.3.1 | Structure & Roof | 4 | Phase 3 | m² | 200 | 200m² garage structure | 180 | 260 | 380 | 36000 | 52000 | 76000 | 20 | 30 | 50 | Steel or blockwork frame, concrete floor, pitched roof, insulated
C1.2.3.2 | Doors & Internal Fitout | 4 | Phase 3 | Item | 1 | Garage doors, electrics, workshop | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 10 | 15 | 25 | 4x electric roller doors, EV charging points, lighting, workshop bench, mezzanine storage
C1.2.3.1.1 | Garage Foundations & Slab | 5 | Phase 3 | m² | 200 | 200m² concrete slab | 55 | 80 | 120 | 11000 | 16000 | 24000 | 5 | 8 | 12 | Reinforced slab, drainage falls
C1.2.3.1.2 | Garage Walls & Structure | 5 | Phase 3 | m² | 200 | Block or steel frame | 120 | 175 | 260 | 24000 | 35000 | 52000 | 10 | 15 | 25 | Blockwork or portal frame structure
C1.2.3.1.3 | Garage Roof | 5 | Phase 3 | m² | 220 | Roof area 220m² | 55 | 85 | 130 | 12100 | 18700 | 28600 | 5 | 8 | 14 | Profiled steel or concrete tile, insulated
C1.2.3.2.1 | Garage Roller Doors x4 | 5 | Phase 3 | Item | 4 | Electric roller doors | 2200 | 3500 | 5500 | 8800 | 14000 | 22000 | 3 | 5 | 8 | Insulated electric roller doors with remote
C1.2.3.2.2 | EV Charging Points | 5 | Phase 3 | Item | 4 | 7kW chargers x4 | 800 | 1200 | 1800 | 3200 | 4800 | 7200 | 2 | 3 | 5 | 7-22kW EV charging points, dedicated circuit
C1.2.3.2.3 | Garage Electrical & Lighting | 5 | Phase 3 | Item | 1 | Full electrical fit | 4500 | 7000 | 12000 | 4500 | 7000 | 12000 | 3 | 5 | 8 | LED lighting, consumer unit, sockets, security
C1.2.4.1 | Foundations & Structure | 4 | Phase 3 | m² | 400 | 400m² total barn footprint | 120 | 180 | 270 | 48000 | 72000 | 108000 | 25 | 35 | 55 | Concrete pad foundations, steel portal frame barns
C1.2.4.2 | Roof & Envelope | 4 | Phase 3 | m² | 450 | Roof + cladding ~450m² | 55 | 85 | 130 | 24750 | 38250 | 58500 | 15 | 22 | 35 | Profiled steel cladding, agricultural roof sheets
C1.2.4.3 | MEP & Electrical | 4 | Phase 3 | Item | 1 | Barn electrical & water supply | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 10 | 15 | 25 | Three phase power, lighting, water supply, drainage
C1.2.4.4 | Internal Fitout & Doors Gates | 4 | Phase 3 | Item | 1 | Barn doors, gates, internal divisions | 15000 | 28000 | 48000 | 15000 | 28000 | 48000 | 10 | 15 | 25 | Large sliding barn doors, livestock pen divisions, gates
C1.2.4.1.1 | Barn 1 Main Agricultural Barn | 5 | Phase 3 | m² | 250 | 250m² main barn | 120 | 175 | 260 | 30000 | 43750 | 65000 | 15 | 22 | 35 | Main stock/equipment barn, concrete pad, portal frame
C1.2.4.1.2 | Barn 2 Storage & Feed Store | 5 | Phase 3 | m² | 150 | 150m² feed/storage barn | 110 | 160 | 240 | 16500 | 24000 | 36000 | 10 | 15 | 25 | Feed store, equipment storage, concrete floor
C1.2.4.4.1 | Large Sliding Barn Doors | 5 | Phase 3 | Item | 4 | 4 sets large sliding doors | 1800 | 3000 | 4800 | 7200 | 12000 | 19200 | 3 | 5 | 8 | Galvanised sliding doors, track, guide posts
C1.2.4.4.2 | Livestock Pen Dividers | 5 | Phase 3 | Item | 1 | Internal pen system | 3500 | 6000 | 10000 | 3500 | 6000 | 10000 | 3 | 5 | 8 | Steel penning for llamas, highland cows
C1.2.4.4.3 | Feed & Hay Storage Fitout | 5 | Phase 3 | Item | 1 | Feed bins, hay storage | 2500 | 4500 | 8000 | 2500 | 4500 | 8000 | 2 | 3 | 5 | Metal feed bins, hay feeders, tack storage
C1.2.5.1 | Fencing & Gates | 4 | Phase 3 | m | 2500 | ~2500m perimeter + field fencing | 18 | 28 | 42 | 45000 | 70000 | 105000 | 20 | 30 | 50 | Post & rail, livestock-proof fencing, field gates. 15 acres.
C1.2.5.2 | Irrigation System & Water Troughs | 4 | Phase 3 | Item | 1 | Borehole-fed irrigation + troughs | 15000 | 28000 | 48000 | 15000 | 28000 | 48000 | 10 | 15 | 25 | Borehole pump, pipework to troughs, irrigation runs to growing areas
C1.2.5.3 | Animal Housing & Coops | 4 | Phase 3 | Item | 1 | Multi species housing | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 15 | 22 | 35 | Chicken coops, duck housing, quail pens, llama/cow field shelter
C1.2.5.4 | Greenhouse & Poly Tunnel | 4 | Phase 3 | Item | 1 | Large greenhouse + poly tunnel | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 10 | 15 | 25 | Commercial greenhouse ~200m², large poly tunnel ~300m²
C1.2.5.5 | Vegetable & Flower Gardens | 4 | Phase 3 | m² | 1500 | ~1500m² growing areas | 8 | 14 | 22 | 12000 | 21000 | 33000 | 10 | 15 | 25 | Raised beds, paths, soil preparation, edging
C1.2.5.6 | Fruit Trees & Orchards | 4 | Phase 3 | Item | 1 | Small orchard ~50 trees | 4500 | 8000 | 14000 | 4500 | 8000 | 14000 | 5 | 8 | 14 | Mixed fruit tree planting, staking, guards, orchard grass
C1.2.5.7 | Farm Equipment & Feed | 4 | Phase 5 | Item | 1 | Initial equipment & startup feed stock | 18000 | 35000 | 65000 | 18000 | 35000 | 65000 | 30 | 45 | 60 | Compact tractor, quad bike, feed, initial livestock purchase
C1.2.5.1.1 | Perimeter Fencing | 5 | Phase 3 | m | 1500 | 1500m boundary post & rail | 20 | 30 | 45 | 30000 | 45000 | 67500 | 10 | 15 | 25 | Post & rail 3-bar fencing, treated timber
C1.2.5.1.2 | Field Subdivision Fencing | 5 | Phase 3 | m | 1000 | 1000m internal field divides | 15 | 24 | 36 | 15000 | 24000 | 36000 | 8 | 12 | 20 | Post & wire or post & rail for field rotation
C1.2.5.1.3 | Farm Gates | 5 | Phase 3 | Item | 12 | Field & access gates x12 | 400 | 700 | 1100 | 4800 | 8400 | 13200 | 3 | 5 | 8 | Galvanised steel field gates, posts, hinges, bolts
C1.2.5.3.1 | Chicken Coops & Run | 5 | Phase 3 | Item | 2 | 2x large chicken setups | 1200 | 2200 | 3800 | 2400 | 4400 | 7600 | 3 | 5 | 8 | Large walk-in coops, enclosed runs, nesting boxes, feeders
C1.2.5.3.2 | Duck Housing | 5 | Phase 3 | Item | 1 | Runner duck house & pond access | 800 | 1500 | 2800 | 800 | 1500 | 2800 | 2 | 3 | 5 | Duck house, ramp, pond access, predator-proof run
C1.2.5.3.3 | Quail Pens | 5 | Phase 3 | Item | 2 | 2x quail pens | 600 | 1100 | 2000 | 1200 | 2200 | 4000 | 2 | 3 | 5 | Raised quail housing, wire mesh, nesting
C1.2.5.3.4 | Llama Field Shelter | 5 | Phase 3 | Item | 1 | 3-bay field shelter | 3500 | 6000 | 10000 | 3500 | 6000 | 10000 | 3 | 5 | 8 | Timber field shelter, concrete base, hay feeder
C1.2.5.3.5 | Highland Cow Shelter & Handling | 5 | Phase 3 | Item | 1 | Cattle shelter + crush/handling | 5500 | 9000 | 16000 | 5500 | 9000 | 16000 | 3 | 5 | 8 | Open-fronted shelter, cattle crush/handling pen
C1.2.5.4.1 | Greenhouse Structure & Glazing | 5 | Phase 3 | m² | 200 | 200m² commercial greenhouse | 55 | 85 | 130 | 11000 | 17000 | 26000 | 5 | 8 | 14 | Aluminium frame, polycarbonate or glass, gutters
C1.2.5.4.2 | Greenhouse Internal Fitout | 5 | Phase 3 | Item | 1 | Staging, irrigation, heating | 5000 | 9000 | 16000 | 5000 | 9000 | 16000 | 3 | 5 | 8 | Staging benches, drip irrigation, propagation area
C1.2.5.4.3 | Poly Tunnel | 5 | Phase 3 | m² | 300 | 300m² poly tunnel | 12 | 20 | 32 | 3600 | 6000 | 9600 | 3 | 5 | 8 | Steel hoops, heavy duty polythene, base rail, doors
C1.2.6.1 | Driveway & External Paving | 4 | Phase 3 | m² | 2000 | 500m x 4m driveway + courtyard | 45 | 75 | 120 | 90000 | 150000 | 240000 | 20 | 30 | 45 | Tarmac drive, block paving courtyard, drainage channels
C1.2.6.2 | Septic Tank & Disposal | 4 | Phase 3 | Item | 1 | Package sewage treatment plant | 10000 | 18000 | 32000 | 10000 | 18000 | 32000 | 5 | 8 | 14 | Klargester or equiv, sized for 10-bed equiv, percolation test, EA permit
C1.2.6.3 | Borehole & Pump | 4 | Phase 3 | Item | 1 | 100m deep borehole + pump | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 5 | 8 | 14 | Drilled borehole for farm water supply, submersible pump, pressure vessel
C1.2.6.4 | Grid Connection & Site Services | 4 | Phase 2-3 | Item | 1 | LV grid connection, rural overhead/underground | 25000 | 45000 | 80000 | 25000 | 45000 | 80000 | 20 | 35 | 60 | DNO connection (rural Devon - potentially long run), temporary site power, telecom
C1.2.6.5 | Site Drainage & Swales | 4 | Phase 3 | m | 500 | 500m of drainage runs + swales | 55 | 85 | 130 | 27500 | 42500 | 65000 | 10 | 15 | 25 | Surface water drainage, swales, soakaways, road drainage
C1.2.7.1 | Garden Landscaping & Paths | 4 | Phase 3 | m² | 8000 | ~8000m² total garden area | 12 | 22 | 38 | 96000 | 176000 | 304000 | 25 | 40 | 60 | Lawn, planting, paths, soil prep, garden design
C1.2.7.2 | Wild Pond & Water Features | 4 | Phase 3 | Item | 1 | Natural wildlife pond ~400m² | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 10 | 15 | 25 | Excavated lined pond, planted margins, wildlife habitat, fountain
C1.2.7.3 | Outdoor Furniture Lighting & Features | 4 | Phase 3 | Item | 1 | Furniture, lighting, sculpture | 15000 | 28000 | 50000 | 15000 | 28000 | 50000 | 5 | 8 | 14 | Teak/stone furniture, LED path lighting, feature lighting, water features
C1.3.1 | Quality Inspections & Handover | 3 | Phase 4 | Item | 1 | Final snagging, inspections | 20000 | 35000 | 60000 | 20000 | 35000 | 60000 | 15 | 25 | 40 | Building control sign-off, snagging survey, handover documentation
C1.3.2 | Commissioning MEP & Utilities | 3 | Phase 4 | Item | 1 | Commission all systems | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 10 | 20 | 35 | HVAC, solar, heating, water, septic, borehole commissioning
C1.4.1 | Property Maintenance Staff (Annual) | 3 | Phase 5 | FTE | 2 | 2x maintenance/housekeeping staff | 28000 | 38000 | 50000 | 56000 | 76000 | 100000 | 365 | 365 | 365 | Housekeeper + handyman/groundskeeper. NLW + oncosts.
C1.4.2 | Utilities & Running Costs (Annual) | 3 | Phase 5 | Year | 1 | Annual utilities | 18000 | 28000 | 45000 | 18000 | 28000 | 45000 | 365 | 365 | 365 | Electricity (offset by solar), heating oil/LPG/ASHP, water rates, broadband, insurance
C1.4.3 | Farm & Animal Care (Annual) | 3 | Phase 5 | Year | 1 | Annual farm running costs | 15000 | 25000 | 42000 | 15000 | 25000 | 42000 | 365 | 365 | 365 | Animal feed (ducks, chickens, llamas, cows, quail), vet bills, farrier, bedding, farm supplies

## Risks
Risk ID | Risk Description | Likelihood |  | D_Low | D_ML | D_High | Low (£) | ML(£) | High(£) | Mitigation
R1 | Supply chain delays for materials | High | Low: 10, Most: 30, High: 60 | 10 | 30 | 60 | 50000 | 150000 | 300000 | Pre-order long-lead items, multiple suppliers, maintain buffer stock
R2 | Extreme weather delays | Medium | Low: 5, Most: 15, High: 30 | 5 | 15 | 30 | 20000 | 50000 | 100000 | Schedule build in optimal weather, cover storage for materials, add schedule buffer
R3 | Labour shortages / strikes | Medium | Low: 10, Most: 25, High: 50 | 10 | 25 | 50 | 30000 | 100000 | 250000 | Lock-in contractors early, cross-train staff, include labour contingency
R4 | Regulatory / permit delays | Medium | Low: 15, Most: 30, High: 60 | 15 | 30 | 60 | 10000 | 50000 | 100000 | Engage local authorities early, submit complete permit applications
R5 | Utility connection delays | Medium | Low: 5, Most: 15, High: 30 | 5 | 15 | 30 | 20000 | 50000 | 100000 | Liaise early with utilities, schedule in parallel, provisional costs for temporary solutions
R6 | Cost escalation for key materials | High | Low: 0, Most: 0, High: 0 | 0 | 0 | 0 | 50000 | 200000 | 500000 | Use parametric models, fixed-price contracts, escalation contingency
R7 | Equipment failure on site | Low | Low: 1, Most: 3, High: 7 | 1 | 3 | 7 | 5000 | 15000 | 50000 | Regular maintenance, backup rental, insurance coverage
R8 | Environmental / ecological issues | Medium | Low: 10, Most: 20, High: 40 | 10 | 20 | 40 | 20000 | 50000 | 150000 | Conduct ecological surveys, adjust design if needed
R9 | Integration issues (sustainable systems) | Medium | Low: 5, Most: 15, High: 30 | 5 | 15 | 30 | 30000 | 100000 | 250000 | Engage experienced MEP engineers, phased commissioning
R10 | Operational risk post-build | Medium | Low: 0, Most: 0, High: 0 | 0 | 0 | 0 | 10000 | 25000 | 50000 | Develop SOPs, train staff, schedule routine maintenance

## Cost_Lines
CBS_Code | CBS_Description | CBS_Level | WBS_Phase | Row_Type | Unit | Qty | Size_Assumption | Unit_Cost_Low (£) | Unit_Cost_ML (£) | Unit_Cost_High (£) | Total_Low (£) | Total_ML (£) | Total_High (£) | Duration_Low (days) | Duration_ML (days) | Duration_High (days) | Notes / Assumptions | Sensitivity_Drivers | Sensitivity_Rationale
C1.1.1 | Planning & Project Management | 3 | Phase 1 | INPUT | Months | 18 | 18-month pre-build programme | 4000 | 7000 | 11000 | 72000 | 126000 | 198000 | 90 | 150 | 240 | PM, planning consultant, architect prelims, programme coordination | LAB, REG | PM/architect day rates; planning delays extend fees
C1.1.2 | Surveys Site Investigations & Permits | 3 | Phase 1-2 | INPUT | Item | 1 | Topo, geo, ecology, planning application | 35000 | 60000 | 95000 | 35000 | 60000 | 95000 | 30 | 60 | 90 | Topographic survey, ground investigation, ecology report, planning app fees, pre-app meetings | LAB, REG | Surveyor rates; ecological/planning conditions can add scope
C1.2.1.1 | Substructure | 4 | Phase 3 | ROLLUP | m² | 800 | 800m² strip/raft foundations | [6 empty] | 30 | 45 | 70 | See L5 breakdown below — rollup of C1.2.1.1.1–5
C1.2.1.1.1 | Site Clearance & Levelling | 5 | Phase 3 | INPUT | m² | 1200 | 1200m² clearance | 8 | 14 | 22 | 9600 | 16800 | 26400 | 5 | 8 | 14 | Strip topsoil, level site, vegetation removal | LAB, FUEL | Plant hire & haulage; rural Devon access costs
C1.2.1.1.2 | Excavation & Earthworks | 5 | Phase 3 | INPUT | m³ | 1500 | ~1500m³ inc basement dig | 28 | 42 | 65 | 42000 | 63000 | 97500 | 8 | 12 | 20 | Bulk excavation, basement dig, spoil removal (rural haulage premium) | MAT, LAB, FUEL | Concrete, rebar; excavation plant; spoil haulage — all volatile
C1.2.1.1.3 | Foundation Concrete & Reinforcement | 5 | Phase 3 | INPUT | m² | 800 | 800m² strip/raft | 85 | 125 | 190 | 68000 | 100000 | 152000 | 10 | 15 | 25 | Concrete foundations, rebar, blinding, formwork | MAT, LAB | Concrete & rebar — steel price sensitive; formwork labour
C1.2.1.1.4 | Ground Floor Slab | 5 | Phase 3 | INPUT | m² | 800 | 800m² insulated slab | 35 | 55 | 80 | 28000 | 44000 | 64000 | 5 | 8 | 14 | Insulated concrete slab with UFH provision | MAT, LAB | Concrete slab; insulation board — petrochemical derived
C1.2.1.1.5 | Damp Proof Course & Tanking | 5 | Phase 3 | INPUT | m² | 800 | DPC + basement tanking 600m² | 18 | 28 | 42 | 14400 | 22400 | 33600 | 3 | 5 | 8 | DPC throughout, full basement tanking system | MAT, LAB, SPEC | Tanking membranes; specialist tanking contractor
C1.2.1.2 | Superstructure Walls | 4 | Phase 3 | INPUT | m² | 800 | External & loadbearing walls | 220 | 320 | 480 | 176000 | 256000 | 384000 | 30 | 50 | 75 | Blockwork/stone clad external, loadbearing internals. Modern trad farmhouse. | MAT, LAB | Blockwork, stone cladding, mortar — all material cost sensitive
C1.2.1.3 | Roof Structure | 4 | Phase 3 | INPUT | m² | 900 | Roof plan ~900m² inc overhangs | 120 | 180 | 280 | 108000 | 162000 | 252000 | 25 | 40 | 60 | Timber roof structure, complex farmhouse pitches, SE input | MAT, LAB | Structural timber — highly volatile (2021 spike +40%); SE fees
C1.2.1.4 | External Envelope | 4 | Phase 3 | INPUT | m² | 900 | Roof covering + external wall finish | 95 | 145 | 220 | 85500 | 130500 | 198000 | 20 | 35 | 55 | Natural slate or clay tile, render/stone facade, windows, ext doors | MAT, LAB, FUEL | Natural slate/clay tile — quarried material; rural delivery
C1.2.1.5 | First Fix MEP | 4 | Phase 3 | INPUT | m² | 800 | 800m² GIA | 75 | 115 | 175 | 60000 | 92000 | 140000 | 20 | 30 | 50 | First fix plumbing, heating pipework, electrical, data/AV cabling | MAT, LAB | Copper pipework, cable — copper price volatile; trade rates
C1.2.1.6 | Internal Walls & Partitions | 4 | Phase 3 | INPUT | m² | 600 | ~600m² partitions | 45 | 70 | 110 | 27000 | 42000 | 66000 | 15 | 25 | 40 | Timber stud and blockwork partitions throughout | MAT, LAB | Blockwork, stud, board — material & trade rates
C1.2.1.7 | Plaster & Insulation | 4 | Phase 3 | INPUT | m² | 800 | 800m² GIA | 40 | 60 | 90 | 32000 | 48000 | 72000 | 20 | 30 | 45 | Full insulation package, plastering throughout | MAT, LAB | Insulation board (petrochemical), plaster, mesh
C1.2.1.8 | Second Fix & Fixtures | 4 | Phase 3 | INPUT | m² | 800 | 800m² GIA | 80 | 130 | 200 | 64000 | 104000 | 160000 | 25 | 40 | 60 | Second fix plumbing, electrical, sanitaryware, radiators/UFH | MAT, LAB, SPEC | Sanitaryware, radiators, second fix trades; high spec items
C1.2.1.9 | Finishes | 4 | Phase 3 | INPUT | m² | 800 | 800m² GIA | 65 | 110 | 180 | 52000 | 88000 | 144000 | 20 | 35 | 55 | Floor finishes, tiling, decoration, joinery finishes throughout | MAT, LAB, SPEC | Tiles, stone flooring, timber flooring — material sensitive
C1.2.1.10 | Basement & Entertainment | 4 | Phase 3 | ROLLUP | m² | 150 | 150m² basement | [6 empty] | 40 | 60 | 90 | See L5 breakdown — rollup of C1.2.1.10.1–5
C1.2.1.10.1 | Basement Structural Shell | 5 | Phase 3 | INPUT | m² | 150 | 150m² tanked shell | 350 | 500 | 780 | 52500 | 75000 | 117000 | 15 | 25 | 40 | Structural walls, tanking, slab, waterproofing | MAT, LAB, SPEC | Specialist tanking; structural concrete; single-source risk
C1.2.1.10.2 | Wine Cellar Fitout | 5 | Phase 3 | INPUT | Item | 1 | ~30m² climate controlled | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | Racking, temp control, tiling, lighting | SPEC, LAB | Bespoke wine racking; climate control unit pricing
C1.2.1.10.3 | Bar Fitout | 5 | Phase 3 | INPUT | Item | 1 | ~25m² bar area | 15000 | 28000 | 48000 | 15000 | 28000 | 48000 | 5 | 8 | 12 | Bespoke bar cabinetry, sink, refrigeration, bar top, backlit shelving | SPEC, LAB, MAT | Bespoke bar cabinetry; stone bar top; appliances
C1.2.1.10.4 | Entertainment Area | 5 | Phase 3 | INPUT | Item | 1 | ~60m² pool table, cinema, seating | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 5 | 8 | 12 | AV system, projector/screen, acoustic panels, pool table, seating | SPEC, ENERGY | AV equipment pricing; energy for climate control
C1.2.1.10.5 | Basement MEP | 5 | Phase 3 | INPUT | Item | 1 | Basement services | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 5 | 8 | 12 | HVAC, lighting, electrical, data, plumbing for basement | MAT, LAB | Standard MEP — copper, cable, ducting
C1.2.1.11 | Kitchen Pantry & Utility | 4 | Phase 3 | ROLLUP | Item | 1 | Large farm kitchen + pantry + utility | [6 empty] | 15 | 25 | 40 | Rollup of C1.2.1.11.1–5
C1.2.1.11.1 | Kitchen Units & Cabinetry | 5 | Phase 3 | INPUT | Item | 1 | Bespoke high spec ~35m² | 28000 | 55000 | 95000 | 28000 | 55000 | 95000 | 5 | 8 | 14 | Bespoke painted Shaker-style, soft close, integrated | SPEC, MAT | Bespoke cabinetry — long lead, single source; timber/paint
C1.2.1.11.2 | Kitchen Appliances | 5 | Phase 3 | INPUT | Item | 1 | Full appliance package | 12000 | 22000 | 40000 | 12000 | 22000 | 40000 | 3 | 5 | 8 | Aga/range, integrated fridge-freezer, dishwasher, wine cooler | SPEC, ENERGY | Aga/range cooker pricing; appliance supply chain
C1.2.1.11.3 | Kitchen Worktops & Sink | 5 | Phase 3 | INPUT | Item | 1 | Stone worktops, butler sink | 5000 | 9000 | 16000 | 5000 | 9000 | 16000 | 2 | 3 | 5 | Quartz or granite, Belfast sink, taps | MAT, SPEC | Quartz/granite — stone pricing; butler sink
C1.2.1.11.4 | Pantry Fitout | 5 | Phase 3 | INPUT | Item | 1 | Walk-in pantry ~12m² | 4500 | 8000 | 14000 | 4500 | 8000 | 14000 | 2 | 3 | 5 | Shelving, worktop, small sink, larder storage | MAT, LAB | Shelving, worktop — standard materials
C1.2.1.11.5 | Utility Room Fitout | 5 | Phase 3 | INPUT | Item | 1 | Walk-in utility ~14m² | 6000 | 10000 | 18000 | 6000 | 10000 | 18000 | 2 | 3 | 5 | Worktops, laundry appliances, sink, storage, boot room | MAT, LAB | Laundry appliances, worktops — standard
C1.2.1.12 | Library Offices & Lounge | 4 | Phase 3 | ROLLUP | Item | 1 | Library, 2x offices, lounge, coffee bar | [6 empty] | 15 | 20 | 35 | Rollup of C1.2.1.12.1–7. Library, 2x offices, lounge, coffee bar, sunroom, guest WCs, wood fireplace.
C1.2.1.12.1 | Library Bespoke Joinery | 5 | Phase 3 | INPUT | Item | 1 | Floor-to-ceiling shelving ~20m² | 12000 | 20000 | 35000 | 12000 | 20000 | 35000 | 5 | 8 | 12 | Bespoke painted shelving, rolling ladder, reading nook | SPEC, MAT | Bespoke joinery — timber, paint; specialist joiner rates
C1.2.1.12.2 | Office Fitout x2 | 5 | Phase 3 | INPUT | Item | 2 | ~14m² each | 4000 | 7000 | 12000 | 8000 | 14000 | 24000 | 3 | 5 | 8 | Fitted desks, storage, data/AV, joinery | MAT, LAB | Standard desk & storage fitout
C1.2.1.12.3 | Lounge Fireplace & Joinery | 5 | Phase 3 | INPUT | Item | 1 | Feature fireplace + joinery | 8000 | 14000 | 24000 | 8000 | 14000 | 24000 | 3 | 5 | 8 | Log burner or open fire, bespoke surround, TV joinery | SPEC, MAT, FUEL | Log burner unit + twin-wall flue; rural delivery of stove
C1.2.1.12.4 | Coffee Bar Fitout | 5 | Phase 3 | INPUT | Item | 1 | ~6m² | 3500 | 6000 | 10000 | 3500 | 6000 | 10000 | 2 | 3 | 5 | Cabinetry, worktop, commercial coffee machine, sink | SPEC, MAT | Commercial coffee machine pricing; cabinetry
C1.2.1.12.5 | Sunroom Fitout | 5 | Phase 3 | INPUT | Item | 1 | ~20m² | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 5 | 8 | 12 | Glazed extension or internal sunroom, bifolds/glazed roof, tiling, blinds | MAT, SPEC | Glazing & bifolds — aluminium/glass pricing
C1.2.1.12.6 | Guest WC Fitout x2 | 5 | Phase 3 | INPUT | Item | 2 | 2x downstairs guest WCs | 1800 | 3200 | 5500 | 3600 | 6400 | 11000 | 2 | 3 | 5 | FR-07: 2 downstairs guest toilets. Tiled, WC, vanity basin, heated towel rail per unit. High spec. | MAT, LAB | Sanitaryware, tiling — standard materials
C1.2.1.12.7 | Wood Fireplace & Flue Installation | 5 | Phase 3 | INPUT | Item | 1 | Feature wood burning stove + flue | 4500 | 7500 | 14000 | 4500 | 7500 | 14000 | 3 | 5 | 8 | FR-01/NFR-11: Log burning stove or open fireplace. Includes register plate, liner, twin-wall flue, hearth, surround. Building regs compliance. | SPEC, MAT, FUEL | Log burner or open fire; flue liner; rural delivery
C1.2.1.13 | Orangery & Outdoor Kitchen | 4 | Phase 3 | ROLLUP | Item | 1 | Garden orangery + outdoor kitchen | [6 empty] | 20 | 30 | 50 | Rollup of C1.2.1.13.1–4
C1.2.1.13.1 | Orangery Structure & Glazing | 5 | Phase 3 | INPUT | m² | 45 | 45m² orangery | 800 | 1300 | 2000 | 36000 | 58500 | 90000 | 10 | 18 | 30 | Hardwood/aluminium frame, roof lantern, large glazed panels | SPEC, MAT | Bespoke glazed structure — aluminium/hardwood; glazing pricing
C1.2.1.13.2 | Orangery Internal Finishes | 5 | Phase 3 | INPUT | Item | 1 | Flooring, plaster, doors | 6000 | 10000 | 18000 | 6000 | 10000 | 18000 | 5 | 8 | 12 | Tiled floor, plastered walls, bifold garden doors | MAT, LAB | Tiling, plastering — standard trades
C1.2.1.13.3 | Outdoor Kitchen Structure & Cover | 5 | Phase 3 | INPUT | Item | 1 | ~20m² covered structure | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | Pergola/roof, stone or render walls | MAT, LAB, FUEL | Pergola/roof structure; rural delivery of materials
C1.2.1.13.4 | Outdoor Kitchen Appliances & Fitout | 5 | Phase 3 | INPUT | Item | 1 | BBQ, sink, fridge, worktops | 6000 | 12000 | 22000 | 6000 | 12000 | 22000 | 3 | 5 | 8 | Built-in BBQ, outdoor fridge, stone worktops, outdoor sink | SPEC, MAT | Built-in BBQ, outdoor fridge — specialist outdoor kitchen
C1.2.1.14 | Solar Panels & Wind Turbines | 4 | Phase 3 | ROLLUP | Item | 1 | ~30kWp solar + wind + battery | [6 empty] | 10 | 15 | 25 | Rollup of C1.2.1.14.1–3
C1.2.1.14.1 | Solar PV Panels | 5 | Phase 3 | INPUT | kWp | 30 | 30kWp array | 900 | 1300 | 1900 | 27000 | 39000 | 57000 | 5 | 8 | 12 | Roof or ground mounted, inverters, mounting | MAT, ENERGY, SPEC | Solar panel pricing — commodity sensitive; inverter supply chain
C1.2.1.14.2 | Battery Storage Packs | 5 | Phase 3 | INPUT | kWh | 30 | 30kWh storage | 600 | 900 | 1400 | 18000 | 27000 | 42000 | 2 | 3 | 5 | Lithium battery packs, BMS, solar integration | MAT, ENERGY, SPEC | Lithium battery pricing — highly volatile; supply chain risk
C1.2.1.14.3 | Small Wind Turbine | 5 | Phase 3 | INPUT | Item | 1 | ~6kW turbine | 12000 | 20000 | 35000 | 12000 | 20000 | 35000 | 5 | 8 | 14 | Planning likely needed, tower, grid tie inverter | SPEC, REG, FUEL | Wind turbine unit + tower; planning consent; crane hire
C1.2.1.15 | Water Collection & Treatment | 4 | Phase 3 | ROLLUP | Item | 1 | Rainwater harvesting + UV treatment | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 7 | 10 | 18 | Rollup of C1.2.1.15.1 (mains) + rainwater harvesting system. FR-43, FR-45.
C1.2.1.15.1 | Mains Water Connection to House | 5 | Phase 3 | INPUT | Item | 1 | South West Water mains connection | 3500 | 7000 | 15000 | 3500 | 7000 | 15000 | 5 | 8 | 14 | FR-45: Mains water supply for main house (separate from farm borehole). SW Water connection charge + groundworks for supply pipe. Rural North Devon — potentially long run. | REG, FUEL | SW Water connection charge variable; groundworks for rural run
C1.2.1.16 | Septic Tank | 4 | Phase 3 | DUPLICATE | Item | 1 | Package sewage treatment plant | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | ⚠️ DUPLICATE REMOVED — see C1.2.6.1/C1.2.6.2 for canonical cost line. Sized for main house, percolation test required, EA permit
C1.2.1.17 | Driveway & Paving | 4 | Phase 3 | DUPLICATE | m² | 2000 | 500m driveway + courtyard ~2000m² | 45 | 75 | 120 | 90000 | 150000 | 240000 | 20 | 30 | 45 | ⚠️ DUPLICATE REMOVED — see C1.2.6.1/C1.2.6.2 for canonical cost line. Tarmac/gravel drive, block paving courtyard
C1.2.1.18 | Garden Landscaping & Hydro Pool | 4 | Phase 3 | ROLLUP | Item | 1 | Formal gardens + hydro pool | [6 empty] | 30 | 45 | 70 | Rollup of C1.2.1.18.1–4
C1.2.1.18.1 | Formal Garden Design & Planting | 5 | Phase 3 | INPUT | m² | 3000 | ~3000m² formal garden | 12 | 22 | 38 | 36000 | 66000 | 114000 | 15 | 25 | 40 | Landscape design, soil prep, planting, turf | MAT, LAB, FUEL | Plants, topsoil, turf — material + delivery; landscape labour
C1.2.1.18.2 | Hard Landscaping Paths & Patios | 5 | Phase 3 | INPUT | m² | 500 | Paths, patios, steps ~500m² | 65 | 110 | 180 | 32500 | 55000 | 90000 | 10 | 15 | 25 | Natural stone or porcelain paving, edging | MAT, LAB, FUEL | Natural stone/porcelain — material sensitive; rural delivery
C1.2.1.18.3 | Hydrotherapy Pool | 5 | Phase 3 | INPUT | Item | 1 | Outdoor hydro pool ~8x4m | 35000 | 60000 | 100000 | 35000 | 60000 | 100000 | 15 | 20 | 35 | Heated pool, jets, filtration, cover, surround | SPEC, MAT | Pool shell + heat pump; specialist pool contractor
C1.2.1.18.4 | Pool Plant Room & Services | 5 | Phase 3 | INPUT | Item | 1 | Plant room for pool equipment | 5000 | 9000 | 16000 | 5000 | 9000 | 16000 | 3 | 5 | 8 | Pump house, heat pump, electrical, plumbing | MAT, LAB, SPEC | Heat pump pricing; plant room build
C1.2.1.19 | Gym Spa Sauna Cold Plunge Yoga Studio | 4 | Phase 3 | ROLLUP | Item | 1 | ~150m² wellness complex | [6 empty] | 30 | 45 | 70 | Rollup of C1.2.1.19.1–6
C1.2.1.19.1 | Gym Structure & Shell | 5 | Phase 3 | INPUT | m² | 60 | ~60m² gym shell | 350 | 500 | 750 | 21000 | 30000 | 45000 | 10 | 15 | 25 | Structure, insulation, floor, windows, doors | MAT, LAB | Standard structure — blockwork, insulation, floor
C1.2.1.19.2 | Gym Fitout & Equipment | 5 | Phase 3 | INPUT | Item | 1 | Weights, cardio, mats | 20000 | 40000 | 70000 | 20000 | 40000 | 70000 | 5 | 8 | 14 | Rubber flooring, squat rack, dumbbells, cardio, mirrors | SPEC, FUEL | Gym equipment supply chain; delivery to rural Devon
C1.2.1.19.3 | Sauna Cabin | 5 | Phase 3 | INPUT | Item | 1 | 4-person sauna | 8000 | 14000 | 22000 | 8000 | 14000 | 22000 | 3 | 5 | 8 | Pre-built or bespoke sauna, heater, benching | SPEC, MAT | Sauna cabin unit pricing; timber
C1.2.1.19.4 | Cold Plunge Tank | 5 | Phase 3 | INPUT | Item | 1 | Cold plunge unit | 4000 | 8000 | 15000 | 4000 | 8000 | 15000 | 2 | 3 | 5 | Stainless or timber cold plunge, chiller unit | SPEC, ENERGY | Cold plunge chiller unit — energy equipment pricing
C1.2.1.19.5 | Yoga & Bike Studio | 5 | Phase 3 | INPUT | Item | 1 | ~30m² dual purpose studio | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 5 | 8 | 12 | Sprung floor, mirrors, AV/sound, bike fixings, storage | MAT, LAB, SPEC | Sprung floor, mirrors, AV — mixed materials & specialist
C1.2.1.19.6 | Spa Shower & Changing | 5 | Phase 3 | INPUT | Item | 1 | Wet room, changing area | 8000 | 14000 | 24000 | 8000 | 14000 | 24000 | 3 | 5 | 8 | Tiled wet room, steam option, vanity, lockers | MAT, LAB | Tiling, sanitaryware, wet room — standard trades
C1.2.2.1 | Annex Substructure & Superstructure | 4 | Phase 3 | INPUT | m² | 240 | 120m² x2 annexes | 220 | 320 | 480 | 52800 | 76800 | 115200 | 25 | 40 | 60 | Foundations, walls, floors — both annexes | MAT, LAB | Blockwork, concrete — standard structure materials
C1.2.2.2 | Annex Roof & Envelope | 4 | Phase 3 | INPUT | m² | 280 | Roof ~140m² per unit x2 | 90 | 140 | 210 | 25200 | 39200 | 58800 | 15 | 25 | 40 | Pitched roof, envelope, windows, doors | MAT, LAB, FUEL | Roof tiles/slate, windows — material + rural delivery
C1.2.2.3 | Annex Internal Fitout & Finishes | 4 | Phase 3 | INPUT | m² | 240 | Full fitout both annexes | 180 | 280 | 420 | 43200 | 67200 | 100800 | 20 | 30 | 50 | Kitchen, bathroom, flooring, decoration, joinery | MAT, LAB, SPEC | Kitchen, bathroom, flooring — mixed material & bespoke
C1.2.2.4 | Annex MEP Systems | 4 | Phase 3 | INPUT | m² | 240 | MEP both annexes | 65 | 100 | 155 | 15600 | 24000 | 37200 | 10 | 15 | 25 | Heating, plumbing, electrical, data | MAT, LAB | Standard MEP — copper, cable, radiators
C1.2.3.1 | Garage Structure & Roof | 4 | Phase 3 | ROLLUP | m² | 200 | 200m² garage | [6 empty] | 20 | 30 | 50 | Rollup of C1.2.3.1.1–3
C1.2.3.1.1 | Garage Foundations & Slab | 5 | Phase 3 | INPUT | m² | 200 | 200m² concrete slab | 55 | 80 | 120 | 11000 | 16000 | 24000 | 5 | 8 | 12 | Reinforced slab, drainage falls | MAT, LAB | Reinforced slab — concrete & rebar
C1.2.3.1.2 | Garage Walls & Structure | 5 | Phase 3 | INPUT | m² | 200 | Block or steel frame | 120 | 175 | 260 | 24000 | 35000 | 52000 | 10 | 15 | 25 | Blockwork or portal frame | MAT, LAB | Blockwork or steel frame — steel price sensitive
C1.2.3.1.3 | Garage Roof | 5 | Phase 3 | INPUT | m² | 220 | Roof area 220m² | 55 | 85 | 130 | 12100 | 18700 | 28600 | 5 | 8 | 14 | Profiled steel or concrete tile, insulated | MAT, LAB, FUEL | Profiled steel cladding — steel pricing; rural delivery
C1.2.3.2 | Garage Doors & Internal Fitout | 4 | Phase 3 | ROLLUP | Item | 1 | Doors, EV charging, electrics | [6 empty] | 10 | 15 | 25 | Rollup of C1.2.3.2.1–3
C1.2.3.2.1 | Garage Roller Doors x4 | 5 | Phase 3 | INPUT | Item | 4 | Electric insulated roller doors | 2200 | 3500 | 5500 | 8800 | 14000 | 22000 | 3 | 5 | 8 | Insulated electric roller doors with remote | SPEC, MAT | Insulated roller door units — supplier pricing
C1.2.3.2.2 | EV Charging Points x4 | 5 | Phase 3 | INPUT | Item | 4 | 7-22kW chargers | 800 | 1200 | 1800 | 3200 | 4800 | 7200 | 2 | 3 | 5 | Dedicated circuit, smart chargers | SPEC, ENERGY | EV charger unit pricing; energy infrastructure
C1.2.3.2.3 | Garage Electrical & Lighting | 5 | Phase 3 | INPUT | Item | 1 | Full electrical fit | 4500 | 7000 | 12000 | 4500 | 7000 | 12000 | 3 | 5 | 8 | LED lighting, consumer unit, sockets, security | MAT, LAB | Standard electrical — cable, consumer unit, LED
C1.2.4.1 | Barn Foundations & Structure | 4 | Phase 3 | ROLLUP | m² | 400 | 400m² total barns | [6 empty] | 25 | 35 | 55 | Rollup of C1.2.4.1.1–2
C1.2.4.1.1 | Barn 1 Main Agricultural Barn | 5 | Phase 3 | INPUT | m² | 250 | 250m² main barn | 120 | 175 | 260 | 30000 | 43750 | 65000 | 15 | 22 | 35 | Main stock/equipment barn, concrete pad, portal frame | MAT, LAB, FUEL | Steel portal frame — steel price highly volatile; rural crane
C1.2.4.1.2 | Barn 2 Storage & Feed Store | 5 | Phase 3 | INPUT | m² | 150 | 150m² feed/storage barn | 110 | 160 | 240 | 16500 | 24000 | 36000 | 10 | 15 | 25 | Feed store, equipment storage, concrete floor | MAT, LAB, FUEL | Smaller barn structure — steel + concrete; delivery
C1.2.4.2 | Barn Roof & Envelope | 4 | Phase 3 | INPUT | m² | 450 | Roof + cladding ~450m² | 55 | 85 | 130 | 24750 | 38250 | 58500 | 15 | 22 | 35 | Profiled steel cladding, agricultural roof sheets | MAT, LAB, FUEL | Profiled steel cladding/roofing — steel sensitive; delivery
C1.2.4.3 | Barn MEP & Electrical | 4 | Phase 3 | INPUT | Item | 1 | Barn electrical & water | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 10 | 15 | 25 | 3-phase power, lighting, water supply, drainage | MAT, LAB | Standard 3-phase electrical; water pipework
C1.2.4.4 | Barn Internal Fitout & Doors Gates | 4 | Phase 3 | ROLLUP | Item | 1 | Barn doors, gates, pens | [6 empty] | 10 | 15 | 25 | Rollup of C1.2.4.4.1–3
C1.2.4.4.1 | Large Sliding Barn Doors x4 | 5 | Phase 3 | INPUT | Item | 4 | 4 sets large sliding doors | 1800 | 3000 | 4800 | 7200 | 12000 | 19200 | 3 | 5 | 8 | Galvanised sliding doors, track, guide posts | MAT, FUEL | Galvanised steel doors — steel pricing; rural delivery
C1.2.4.4.2 | Livestock Pen Dividers | 5 | Phase 3 | INPUT | Item | 1 | Internal pen system | 3500 | 6000 | 10000 | 3500 | 6000 | 10000 | 3 | 5 | 8 | Steel penning for llamas, highland cows | MAT, LAB | Steel penning — standard agricultural steelwork
C1.2.4.4.3 | Feed & Hay Storage Fitout | 5 | Phase 3 | INPUT | Item | 1 | Feed bins, hay storage | 2500 | 4500 | 8000 | 2500 | 4500 | 8000 | 2 | 3 | 5 | Metal feed bins, hay feeders, tack storage | MAT, FUEL | Metal feed bins — standard; rural delivery
C1.2.5.1 | Fencing & Gates | 4 | Phase 3 | ROLLUP | m | 2500 | ~2500m fencing + gates | [6 empty] | 20 | 30 | 50 | Rollup of C1.2.5.1.1–3
C1.2.5.1.1 | Perimeter Fencing | 5 | Phase 3 | INPUT | m | 1500 | 1500m boundary post & rail | 20 | 30 | 45 | 30000 | 45000 | 67500 | 10 | 15 | 25 | Post & rail 3-bar, treated timber | MAT, LAB, FUEL | Treated timber posts & rails — timber pricing; rural delivery
C1.2.5.1.2 | Field Subdivision Fencing | 5 | Phase 3 | INPUT | m | 1000 | 1000m internal divides | 15 | 24 | 36 | 15000 | 24000 | 36000 | 8 | 12 | 20 | Post & wire for field rotation | MAT, LAB, FUEL | Post & wire — timber + steel wire; labour on rough ground
C1.2.5.1.3 | Farm Gates x12 | 5 | Phase 3 | INPUT | Item | 12 | Field & access gates | 400 | 700 | 1100 | 4800 | 8400 | 13200 | 3 | 5 | 8 | Galvanised steel field gates, posts, hinges | MAT, FUEL | Galvanised gates — steel pricing; rural delivery
C1.2.5.2 | Irrigation System & Water Troughs | 4 | Phase 3 | INPUT | Item | 1 | Borehole-fed irrigation + troughs | 15000 | 28000 | 48000 | 15000 | 28000 | 48000 | 10 | 15 | 25 | Borehole pump, pipework to troughs, irrigation runs | MAT, LAB, FUEL | Poly pipe, fittings, pump — rural installation labour
C1.2.5.3 | Animal Housing & Coops | 4 | Phase 3 | ROLLUP | Item | 1 | Multi-species animal housing | [6 empty] | 15 | 22 | 35 | Rollup of C1.2.5.3.1–5
C1.2.5.3.1 | Chicken Coops & Run x2 | 5 | Phase 3 | INPUT | Item | 2 | 2x large chicken setups | 1200 | 2200 | 3800 | 2400 | 4400 | 7600 | 3 | 5 | 8 | Walk-in coops, enclosed runs, nesting boxes, feeders | MAT, SPEC | Bespoke coops — timber; specialist supplier
C1.2.5.3.2 | Duck Housing | 5 | Phase 3 | INPUT | Item | 1 | Runner duck house & pond access | 800 | 1500 | 2800 | 800 | 1500 | 2800 | 2 | 3 | 5 | Duck house, ramp, pond access, predator-proof run | MAT, SPEC | Duck housing — timber; specialist supplier
C1.2.5.3.3 | Quail Pens x2 | 5 | Phase 3 | INPUT | Item | 2 | 2x quail pens | 600 | 1100 | 2000 | 1200 | 2200 | 4000 | 2 | 3 | 5 | Raised quail housing, wire mesh, nesting | MAT, SPEC | Quail pens — wire mesh; specialist
C1.2.5.3.4 | Llama Field Shelter | 5 | Phase 3 | INPUT | Item | 1 | 3-bay field shelter | 3500 | 6000 | 10000 | 3500 | 6000 | 10000 | 3 | 5 | 8 | Timber shelter, concrete base, hay feeder | MAT, LAB, FUEL | Timber shelter — treated timber pricing; rural delivery
C1.2.5.3.5 | Highland Cow Shelter & Handling | 5 | Phase 3 | INPUT | Item | 1 | Cattle shelter + crush | 5500 | 9000 | 16000 | 5500 | 9000 | 16000 | 3 | 5 | 8 | Open-fronted shelter, cattle crush/handling pen | MAT, LAB, SPEC | Cattle shelter + crush — steel handling equipment
C1.2.5.4 | Greenhouse & Poly Tunnel | 4 | Phase 3 | ROLLUP | Item | 1 | Greenhouse + poly tunnel | [6 empty] | 10 | 15 | 25 | Rollup of C1.2.5.4.1–3
C1.2.5.4.1 | Greenhouse Structure & Glazing | 5 | Phase 3 | INPUT | m² | 200 | 200m² commercial greenhouse | 55 | 85 | 130 | 11000 | 17000 | 26000 | 5 | 8 | 14 | Aluminium frame, polycarbonate or glass | MAT, SPEC, FUEL | Aluminium greenhouse — specialist supplier; rural delivery
C1.2.5.4.2 | Greenhouse Internal Fitout | 5 | Phase 3 | INPUT | Item | 1 | Staging, irrigation, heating | 5000 | 9000 | 16000 | 5000 | 9000 | 16000 | 3 | 5 | 8 | Staging benches, drip irrigation, propagation area | MAT, LAB | Staging, drip irrigation — standard horticultural
C1.2.5.4.3 | Poly Tunnel | 5 | Phase 3 | INPUT | m² | 300 | 300m² poly tunnel | 12 | 20 | 32 | 3600 | 6000 | 9600 | 3 | 5 | 8 | Steel hoops, heavy duty polythene, base rail, doors | MAT, FUEL | Polythene + hoops — material & delivery sensitive
C1.2.5.5 | Vegetable & Flower Gardens | 4 | Phase 3 | INPUT | m² | 1500 | ~1500m² growing areas | 8 | 14 | 22 | 12000 | 21000 | 33000 | 10 | 15 | 25 | Raised beds, paths, soil prep, edging | MAT, LAB, FUEL | Raised beds, soil, compost — material & rural delivery
C1.2.5.6 | Fruit Trees & Orchards | 4 | Phase 3 | INPUT | Item | 1 | Small orchard ~50 trees | 4500 | 8000 | 14000 | 4500 | 8000 | 14000 | 5 | 8 | 14 | Mixed fruit trees, staking, guards, orchard grass | MAT, FUEL | Fruit tree stock pricing; rural delivery & planting
C1.2.5.7 | Farm Equipment & Feed (startup) | 4 | Phase 5 | INPUT | Item | 1 | Initial equipment + feed stock | 18000 | 35000 | 65000 | 18000 | 35000 | 65000 | 30 | 45 | 60 | Compact tractor, quad bike, feed, initial livestock purchase | SPEC, FUEL, ENERGY | Tractor/quad — equipment pricing; fuel costs to run
C1.2.6.1 | Driveway & External Paving | 4 | Phase 3 | INPUT | m² | 2000 | 500m drive + courtyard | 45 | 75 | 120 | 90000 | 150000 | 240000 | 20 | 30 | 45 | Tarmac/gravel drive, block paving courtyard, drainage | MAT, LAB, FUEL | Tarmac — bitumen oil price sensitive; rural delivery premium
C1.2.6.2 | Septic Tank & Disposal | 4 | Phase 3 | INPUT | Item | 1 | Package sewage treatment plant | 10000 | 18000 | 32000 | 10000 | 18000 | 32000 | 5 | 8 | 14 | Klargester or equiv, EA permit, percolation test | SPEC, REG | Treatment plant unit; EA permit; percolation conditions
C1.2.6.3 | Borehole & Pump | 4 | Phase 3 | INPUT | Item | 1 | 100m deep borehole + pump | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | 5 | 8 | 14 | Drilled borehole, submersible pump, pressure vessel | SPEC, LAB | Specialist driller rates; casing/pump materials
C1.2.6.4 | Grid Connection & Site Services | 4 | Phase 2-3 | INPUT | Item | 1 | LV grid connection rural | 25000 | 45000 | 80000 | 25000 | 45000 | 80000 | 20 | 35 | 60 | DNO connection (rural Devon — long run risk), temp site power, telecom | REG, SPEC, FUEL | DNO connection charge — highly variable rural; cable pricing
C1.2.6.5 | Site Drainage & Swales | 4 | Phase 3 | INPUT | m | 500 | 500m drainage runs + swales | 55 | 85 | 130 | 27500 | 42500 | 65000 | 10 | 15 | 25 | Surface water drainage, swales, soakaways, road drainage | MAT, LAB, FUEL | Drainage pipe, aggregate — material & rural haulage
C1.2.6.6 | Site Security — CCTV Access Control & Alarm | 4 | Phase 3 | INPUT | Item | 1 | Full rural site security system | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | 5 | 8 | 14 | NFR-40: Rural physical security. CCTV cameras (8-12 cameras), NVR, electric gate with intercom/keypad, PIR alarm system, external lighting. Remote monitoring. | SPEC, MAT | CCTV/alarm equipment pricing; gate automation
C1.2.7.1 | Garden Landscaping & Paths | 4 | Phase 3 | INPUT | m² | 8000 | ~8000m² total garden | 12 | 22 | 38 | 96000 | 176000 | 304000 | 25 | 40 | 60 | Lawn, planting, paths, soil prep, garden design | MAT, LAB, FUEL | Topsoil, plants, turf — material + rural delivery; landscape labour
C1.2.7.2 | Wild Pond & Water Features | 4 | Phase 3 | INPUT | Item | 1 | Natural wildlife pond ~400m² | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 10 | 15 | 25 | Excavated lined pond, planted margins, wildlife habitat | MAT, LAB, FUEL | Liner, aggregate, plants — material & rural delivery
C1.2.7.3 | Outdoor Furniture Lighting & Features | 4 | Phase 3 | INPUT | Item | 1 | Furniture, lighting, sculpture | 15000 | 28000 | 50000 | 15000 | 28000 | 50000 | 5 | 8 | 14 | Teak/stone furniture, LED path lighting, water features | SPEC, FUEL | Outdoor furniture — specialist; rural delivery
C1.3.1 | Quality Inspections & Handover | 3 | Phase 4 | INPUT | Item | 1 | Snagging, inspections, sign-off | 20000 | 35000 | 60000 | 20000 | 35000 | 60000 | 15 | 25 | 40 | Building control, snagging survey, handover docs | LAB, REG | Inspector/surveyor rates; building control conditions
C1.3.2 | Commissioning MEP & Utilities | 3 | Phase 4 | INPUT | Item | 1 | Commission all systems | 18000 | 32000 | 55000 | 18000 | 32000 | 55000 | 10 | 20 | 35 | HVAC, solar, heating, water, septic, borehole commissioning | LAB, SPEC | Commissioning engineer rates; specialist system knowledge
C1.4.1 | Property Maintenance Staff (Annual) | 3 | Phase 5 | INPUT | FTE | 2 | Housekeeper + groundskeeper | 28000 | 38000 | 50000 | 56000 | 76000 | 100000 | 365 | 365 | 365 | NLW + oncosts. 2x FTE. | LAB | Staff wages — NLW increases, rural labour market
C1.4.2 | Utilities & Running Costs (Annual) | 3 | Phase 5 | INPUT | Year | 1 | Annual utilities | 18000 | 28000 | 45000 | 18000 | 28000 | 45000 | 365 | 365 | 365 | Electricity (offset solar), heating, water rates, broadband, insurance | ENERGY, REG | Energy tariffs — highly volatile; water rates; insurance
C1.4.3 | Farm & Animal Care (Annual) | 3 | Phase 5 | INPUT | Year | 1 | Annual farm costs | 15000 | 25000 | 42000 | 15000 | 25000 | 42000 | 365 | 365 | 365 | Feed (ducks, chickens, llamas, cows, quail), vet, farrier, bedding, supplies | MAT, FUEL, SPEC | Feed prices — agricultural commodity; vet/farrier costs
KEY: | Level 3 (rollup) | Level 4 (rollup/input) | Level 5 INPUT | ROLLUP (no direct cost)

## Parametric_Benchmarks
Category | Sub-Category | Benchmark_Basis | Unit | Qty_Assumption | Size_Note | Rate_Low (£/unit) | Rate_ML (£/unit) | Rate_High (£/unit) | Parametric_Low (£) | Parametric_ML (£) | Parametric_High (£) | Source_Basis | Notes
Main House | Full Build — Shell & Core | £/m² GIA | m² | 800 | 800m² GIA assumed | 1800 | 2500 | 3500 | 1440000 | 2000000 | 2800000 | BCIS / Homebuilding & Renovating 2024 | High spec modern farmhouse. Includes structure, envelope, M&E, fit-out. Excl. external works.
Main House | Substructure Only | £/m² GIA | m² | 800 | Strip/raft foundations | 180 | 260 | 400 | 144000 | 208000 | 320000 | BCIS Element Cost Guide | Foundation type subject to ground investigation results
Main House | Superstructure Only | £/m² GIA | m² | 800 | Walls, roof, envelope | 350 | 500 | 720 | 280000 | 400000 | 576000 | BCIS Element Cost Guide | External walls, roof structure and covering, windows, ext doors
Main House | Internal Fit-Out | £/m² GIA | m² | 800 | High spec internal fitout | 600 | 900 | 1400 | 480000 | 720000 | 1120000 | Homebuilding & Renovating / industry est. | Kitchen, bathrooms, joinery, finishes, fixtures
Main House | MEP (M&E Services) | £/m² GIA | m² | 800 | Full MEP package | 350 | 500 | 700 | 280000 | 400000 | 560000 | CIBSE / industry benchmark | Heating, plumbing, electrical, renewables, data/AV
Main House | Basement Premium | £/m² basement | m² | 150 | 150m² tanked basement | 800 | 1200 | 1800 | 120000 | 180000 | 270000 | BCIS / structural engineer est. | Premium over standard build for tanked basement construction
Annexes x2 | Full Build per Annex | £/m² GIA | m² | 120 | 120m² per annex | 1200 | 1700 | 2400 | 144000 | 204000 | 288000 | BCIS / self-build benchmarks | Bungalow style, good spec. Per unit — multiply x2 for both
Annexes x2 | Both Annexes Combined | £/m² GIA | m² | 240 | 240m² total both | 1200 | 1700 | 2400 | 288000 | 408000 | 576000 | BCIS / self-build benchmarks | Combined both annexes
Garage | Large Detached Garage | £/m² | m² | 200 | 200m² detached garage | 400 | 650 | 950 | 80000 | 130000 | 190000 | Self-build / builder quotes | Includes structure, roof, doors, basic electrical. EV charging extra.
Barns | Agricultural Portal Frame Barn | £/m² | m² | 400 | 400m² total barn footprint | 280 | 420 | 620 | 112000 | 168000 | 248000 | Agricultural building suppliers | Steel portal frame, profiled cladding, concrete floor
Farm Infrastructure | Fencing — Post & Rail | £/m | m | 2500 | ~2500m total fencing | 18 | 28 | 42 | 45000 | 70000 | 105000 | Fencing contractor benchmarks | 3-bar post & rail, treated softwood
Farm Infrastructure | Irrigation & Troughs | £/acre | acre | 15 | 15 acres farm | 800 | 1400 | 2200 | 12000 | 21000 | 33000 | Agricultural irrigation suppliers | Borehole-fed system, poly pipe, troughs
Farm Infrastructure | Greenhouse — Commercial | £/m² | m² | 200 | 200m² aluminium greenhouse | 55 | 85 | 130 | 11000 | 17000 | 26000 | Commercial greenhouse suppliers | Aluminium frame, polycarbonate glazing
Farm Infrastructure | Poly Tunnel | £/m² | m² | 300 | 300m² poly tunnel | 12 | 20 | 32 | 3600 | 6000 | 9600 | UK poly tunnel suppliers | Steel hoops, HD polythene cover
Landscaping | Garden Landscaping | £/m² | m² | 8000 | ~8000m² total garden area | 12 | 22 | 38 | 96000 | 176000 | 304000 | Landscape contractor benchmarks | Turf, planting, paths, soil prep. Excludes hard landscaping.
Landscaping | Hard Landscaping | £/m² | m² | 500 | Patios, paths, steps | 65 | 110 | 180 | 32500 | 55000 | 90000 | Landscaping contractor benchmarks | Natural stone or porcelain, edging, steps
Landscaping | Wild Pond | £/m² | m² | 400 | ~400m² natural pond | 35 | 65 | 110 | 14000 | 26000 | 44000 | Pond contractor benchmarks | Excavation, lining, planted margins
Landscaping | Driveway — Tarmac/Gravel | £/m² | m² | 2000 | 500m x 4m driveway + court | 45 | 75 | 120 | 90000 | 150000 | 240000 | Driveway contractor benchmarks | Tarmac base, gravel or bound surface finish
Utilities | Septic / Treatment Plant | £/item | Item | 1 | Package treatment plant | 8000 | 15000 | 28000 | 8000 | 15000 | 28000 | Water treatment suppliers | Klargester or equiv. EA permit required.
Utilities | Borehole | £/item | Item | 1 | 100m+ borehole | 12000 | 22000 | 38000 | 12000 | 22000 | 38000 | Borehole drillers (SW England) | Depth dependent. SW England geology typically 60-120m.
Utilities | Grid Connection — Rural | £/item | Item | 1 | Rural DNO connection | 20000 | 40000 | 75000 | 20000 | 40000 | 75000 | DNO indicative / Western Power | Rural Devon — potentially long cable run. DNO quote essential.
Utilities | Solar PV | £/kWp | kWp | 30 | 30kWp system | 900 | 1300 | 1900 | 27000 | 39000 | 57000 | Solar installer benchmarks 2024 | Includes panels, inverter, mounting. Battery extra.
Utilities | Battery Storage | £/kWh | kWh | 30 | 30kWh storage | 600 | 900 | 1400 | 18000 | 27000 | 42000 | Battery storage suppliers 2024 | Lithium LFP, BMS, integration
Utilities | Small Wind Turbine | £/item | Item | 1 | ~6kW micro wind | 12000 | 20000 | 35000 | 12000 | 20000 | 35000 | Wind turbine suppliers | Planning permission likely needed in Devon
Wellness | Gym & Wellness Complex | £/m² | m² | 150 | ~150m² total wellness | 800 | 1300 | 2100 | 120000 | 195000 | 315000 | Gym fit-out specialists | Sauna, cold plunge, yoga, bike studio, changing. High spec.
Wellness | Outdoor Hydrotherapy Pool | £/item | Item | 1 | 8x4m heated outdoor pool | 35000 | 60000 | 100000 | 35000 | 60000 | 100000 | Pool contractor benchmarks | Heated, jets, filtration, cover, surround. Not a swimming pool.
Pre-Construction | Architect Fees | % of build cost | % | 1 | Typically 8-15% of build cost | 80000 | 130000 | 220000 | 80000 | 130000 | 220000 | RIBA fee guide | Full service from concept to completion
Pre-Construction | Project Management | % of build cost | % | 1 | Typically 3-6% of build cost | 35000 | 65000 | 120000 | 35000 | 65000 | 120000 | PM benchmarks | External PM for full build programme
Pre-Construction | Surveys & Planning | £/item | Item | 1 | All pre-construction surveys | 35000 | 60000 | 95000 | 35000 | 60000 | 95000 | Surveyor / planning consultant | Topo, geo, ecology, planning application, pre-app
In-Service (Annual) | Housekeeping & Maintenance Staff | £/FTE/yr | FTE | 2 | 2x FTE staff | 28000 | 38000 | 50000 | 56000 | 76000 | 100000 | ONS / recruitment benchmarks | Housekeeper + groundskeeper. Incl. NI, pension.
In-Service (Annual) | Utilities (Energy, Water, Comms) | £/yr | Year | 1 | Annual utilities | 18000 | 28000 | 45000 | 18000 | 28000 | 45000 | Industry benchmark / energy tariffs | Electricity (net of solar), heating, water, broadband, phone
In-Service (Annual) | Farm & Animal Running Costs | £/yr | Year | 1 | Annual farm costs | 15000 | 25000 | 42000 | 15000 | 25000 | 42000 | Farming benchmarks | Feed, vet, farrier, bedding, equipment maintenance

## Deposit_Schedule
CBS_Code | Item_Description | Phase | Category | Estimated_Total_ML (£) | Deposit_Rate | Deposit_Amount (£) | Months_Before_Delivery | Trigger_Event | Notes
C1.1.1 | Planning & Project Management | Phase 1 | Professional Fees | 126000 | 20% | 25200 | 6 | Appoint PM & Lead Architect | Major — retainer/mobilisation fee
C1.1.2 | Surveys & Permits | Phase 1 | Professional Fees | 60000 | 20% | 12000 | 3 | Survey instruction issued | Medium — survey firm mobilisation
C1.2.1.1 | Substructure Works | Phase 3 | Main Contractor | 208000 | 20% | 41600 | 6 | Main contractor appointed | Major — contractor mobilisation
C1.2.1.2 | Superstructure Walls | Phase 3 | Main Contractor | 256000 | 20% | 51200 | 6 | Structure package awarded | Major — masonry/frame contractor
C1.2.1.3 | Roof Structure | Phase 3 | Specialist Sub | 162000 | 20% | 32400 | 6 | Roof package awarded | Major — timber frame/roof contractor
C1.2.1.4 | External Envelope | Phase 3 | Specialist Sub | 130500 | 20% | 26100 | 6 | Cladding/glazing order placed | Major — slate/stone/windows lead time 4-6 months
C1.2.1.10 | Basement Shell & Fitout | Phase 3 | Specialist Sub | 330000 | 20% | 66000 | 6 | Basement contractor appointed | Major — specialist tanking contractor
C1.2.1.11 | Kitchen Pantry & Utility | Phase 3 | Specialist Supplier | 132000 | 20% | 26400 | 6 | Kitchen design sign-off | Major — bespoke kitchens 6-9 month lead time
C1.2.1.13 | Orangery & Outdoor Kitchen | Phase 3 | Specialist Supplier | 90000 | 20% | 18000 | 6 | Orangery manufacturer order | Major — bespoke glazed structure 5-6 month lead
C1.2.1.14 | Solar PV + Wind + Battery | Phase 3 | Renewable Supplier | 101000 | 20% | 20200 | 6 | System design sign-off | Major — equipment procurement & grid approval
C1.2.1.18 | Garden & Hydro Pool | Phase 3 | Landscape/Pool | 186000 | 20% | 37200 | 6 | Pool contractor appointed | Major — pool manufacture + landscape design
C1.2.1.19 | Gym & Wellness Complex | Phase 3 | Specialist Fitout | 224000 | 20% | 44800 | 6 | Gym fitout contractor signed | Major — sauna, cold plunge bespoke items
C1.2.2 | Annexes x2 | Phase 3 | Main Contractor | 244000 | 20% | 48800 | 6 | Annex contractor appointed | Major — separate package if not main contractor
C1.2.3 | Garage | Phase 3 | Main Contractor | 130000 | 20% | 26000 | 6 | Garage package awarded | Major — structure + doors package
C1.2.4 | Barns & Outbuildings | Phase 3 | Agricultural Supplier | 168000 | 20% | 33600 | 6 | Steel frame order placed | Major — steel portal frame 14-18 week lead time
C1.2.5.1 | Fencing & Gates | Phase 3 | Fencing Contractor | 70000 | 10% | 7000 | 3 | Fencing contractor instruction | Medium — materials + labour
C1.2.5.2 | Irrigation System | Phase 3 | Irrigation Supplier | 28000 | 10% | 2800 | 3 | Irrigation design approved | Medium — pumps and pipework
C1.2.5.3 | Animal Housing & Coops | Phase 3 | Specialist Supplier | 22100 | 10% | 2210 | 3 | Housing order placed | Medium — bespoke animal housing
C1.2.5.4 | Greenhouse & Poly Tunnel | Phase 3 | Greenhouse Supplier | 32000 | 20% | 6400 | 6 | Greenhouse order placed | Major — commercial greenhouse 12-16 week lead
C1.2.6.3 | Borehole & Pump | Phase 3 | Drilling Contractor | 22000 | 20% | 4400 | 6 | Drilling contractor booked | Major — specialist drillers, rural Devon limited availability
C1.2.6.4 | Grid Connection | Phase 3 | DNO / Electrical | 45000 | 20% | 9000 | 6 | DNO application submitted | Major — Western Power Distribution, rural connection can take 6-12 months
C1.2.6.6 | Site Security System | Phase 3 | Security Installer | 15000 | 10% | 1500 | 3 | Security design sign-off | Medium — CCTV, alarm, access gate
C1.3.1 | Quality Inspections & Handover | Phase 4 | Professional Fees | 35000 | 10% | 3500 | 3 | Building control pre-inspection | Medium — inspector fees
C1.3.2 | Commissioning MEP & Utilities | Phase 4 | Specialist | 32000 | 10% | 3200 | 3 | Commissioning programme agreed | Medium — commissioning engineers
TOTAL DEPOSITS REQUIRED | [5 empty] | 549510
Assumption A-06: Major items (>£20k total) = 20% deposit 6 months prior to manufacture/delivery. Medium items (£5k-£20k) = 10% deposit 3 months prior. Minor items (<£5k) excluded from deposit tracking.
Note: Deposit amounts based on Most Likely (ML) total estimates. All deposits are at risk until delivery — recommend deposit protection clauses in all contracts.

## Sensitivity_Scenarios
Sensitivity Analysis — Driver Scenarios (Based on 20-Year Market Spike History)
Scenario uplifts are derived from observed UK market spikes 2004–2024 (top 5 spike events averaged). Apply each driver scenario independently in your Monte Carlo re-run, then combine for a combined stress scenario.
Driver | Driver_Code | Top 5 Spike Events (UK, 2004-2024) | Avg Spike % | Low Sensitivity % | Base (no change) % | High Sensitivity % | Apply To (CBS Lines) | Monte Carlo Action | Notes / Risks
Materials | MAT | 2008 steel +38%; 2011 copper +45%; 2021 timber +43%; 2022 steel +55%; 2022 insulation/board +35% | +43% avg | + 15% | 0% (base) | + 40% | C1.2.1.1.2/.3/.4, C1.2.1.2/.3/.4, C1.2.1.6/.7, C1.2.4.1, C1.2.6.1 and all MAT-tagged lines | Increase Unit_Cost_High by 40% for all MAT-tagged INPUT rows. Re-run MC. Compare P50 to base. | Timber & steel most volatile. Concrete follows fuel. Worst case: simultaneous spikes across all materials.
Labour | LAB | 2008 construction wages +18%; 2017 skills shortage +22%; 2021 post-Brexit +28%; 2022 cost-of-living +19%; 2023 NLW +9.7% | +19% avg | + 10% | 0% (base) | + 25% | All LAB-tagged lines — particularly C1.1.1, C1.2.1.x trade lines, C1.3.x, C1.4.1 | Increase Unit_Cost_High by 25% for all LAB-tagged INPUT rows. Re-run MC. Compare P50 to base. | Rural Devon has thinner labour pool — skilled trades (plasterers, joiners, roofers) at premium. Post-Brexit reduction in EU labour most impactful for finishing trades.
Fuel & Logistics | FUEL | 2008 diesel +65%; 2011 oil +40%; 2014 rural haulage +28%; 2022 diesel +67%; 2022 plant hire +35% | +47% avg | + 15% | 0% (base) | + 50% | All FUEL-tagged lines — driveway, delivery-heavy items, rural haulage surcharges, plant hire | Increase Unit_Cost_High by 50% for all FUEL-tagged INPUT rows. Re-run MC. Compare P50 to base. | Rural North Devon compounds this — single-track road access, long runs from supply depots. 2022 diesel spike most severe in 20 years. Transportation of heavy materials (slate, stone, steel) most exposed.
Specialist / Bespoke Suppliers | SPEC | 2008 bespoke joinery +25%; 2021 kitchen lead times +40%; 2022 glazing +38%; 2022 pool equipment +42%; 2023 sauna/wellness +30% | +35% avg | + 10% | 0% (base) | + 35% | All SPEC-tagged lines — kitchen, orangery, basement fitout, pool, sauna, cold plunge, bespoke joinery | Increase Unit_Cost_High by 35% for all SPEC-tagged INPUT rows. Re-run MC. Compare P50 to base. | Single-source risk — some items have 1-2 UK suppliers (bespoke orangery manufacturers, specialist pool installers). Supply chain disruption can cause both price spikes and programme delays simultaneously.
Energy Prices | ENERGY | 2008 electricity +38%; 2013 gas +40%; 2018 grid charges +22%; 2022 electricity +178%; 2023 normalisation -45% | +56% avg (exc. 2022 outlier: +35% avg) | + 10% | 0% (base) | + 35% | C1.4.2 (running costs), C1.2.1.14.1/.2, C1.2.3.2.2, C1.2.1.19.4 and all ENERGY-tagged lines | Apply to in-service annual running cost lines and energy equipment procurement lines. Re-run MC for in-service phase. | 2022 was an extreme outlier (+178%). Using +35% as high scenario is prudent but note tail risk. Solar/battery/wind offset partially mitigates this — model net grid draw reduction from renewables.
Regulatory / Permitting | REG | 2011 planning condition costs +30%; 2015 CIL charges; 2019 EA permit tightening; 2022 biodiversity net gain; 2024 nutrient neutrality rules | +25% avg | + 5% | 0% (base) | + 30% | C1.1.1, C1.1.2, C1.2.1.15/.16, C1.2.6.2/.4, C1.3.1/.2 and all REG-tagged lines | Apply % uplift to all REG-tagged lines. Also model programme delay risk (+4-8 weeks per condition). Re-run MC. | North Devon specific: AONB proximity, nutrient neutrality (Taw/Torridge catchment), ecology surveys can delay planning. DNO connection charge is the single largest REG risk — rural connection quotes vary enormously.
Combined Stress Scenario | ALL | Simultaneous spike across all drivers — worst case (2022 analogue year) | +30-50% across all | + 15% all drivers | 0% (base) | MAT+35%, LAB+20%, FUEL+40%, SPEC+30%, ENERGY+30%, REG+20% | All INPUT lines — apply driver-specific uplift to each tagged line | Run MC with all driver High scenarios applied simultaneously. Compare combined P50 and P90 to base. This is your stress test / worst case — expect P90 to be 60-80% above base ML estimate. | 2022 was the closest real-world analogue — simultaneous energy, materials, labour and logistics spikes. Recommend holding 20-25% contingency reserve against this scenario.
HOW TO USE THIS TAB WITH YOUR MONTE CARLO:
1. Take your base MC run (Low/ML/High from Cost_Lines tab) as the baseline — record P10, P50, P90.
2. For each sensitivity scenario: apply the High Sensitivity % uplift to the Unit_Cost_High of all tagged INPUT rows.
The Low and ML values stay unchanged — you are widening the right tail of the triangular distribution only.
3. Re-run your Monte Carlo with the adjusted High values. Record the new P10, P50, P90.
4. The difference between base P50 and scenario P50 = the cost impact of that driver spike.
5. Plot results as a Tornado Chart: drivers on Y-axis, £ swing on X-axis — shows which driver moves the number most.
6. Run the Combined Stress Scenario last — this is your overall worst-case envelope.
7. The gap between base P90 and combined stress P90 = your maximum contingency reserve requirement.

## Programme_Gantt
Ranch Build Programme — Indicative Gantt (36 Months)
Work Stream | Cat | Notes / Parallel Assumption | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Phase 1: Planning & Coordination | PHASE | bar: M1 to M6
PM Appointment & Brief | P1 | bar: M1 to M2
Pre-app & Ecology Surveys | P1 | bar: M1 to M4
Topographic & Ground Investigation | P1 | bar: M2 to M4
Planning Application | P1 | Submission + determination period | bar: M2 to M5
Phase 2: Design, Manufacture & Procurement | PHASE | Overlaps Phase 1 from M3 | bar: M3 to M12
Architectural Design (RIBA 2-3) | P2 | bar: M3 to M7
Structural & MEP Engineering | P2 | bar: M5 to M9
Contractor Tendering & Appointment | P2 | bar: M7 to M11
DNO Grid Connection Application | P2 | Rural Devon 6-12 month DNO process | bar: M3 to M12
Long Lead: Kitchen / Orangery / Steel | P2 | 6-9 month bespoke lead times | bar: M6 to M12
Long Lead: Solar / Wind / Battery | P2 | Equipment + grid approval | bar: M6 to M11
Long Lead: Greenhouse | P2 | 12-16 week lead | bar: M7 to M12
Phase 3: Build Execution | PHASE | ~24 month build — 6 parallel streams at peak | bar: M10 to M33
── UTILITIES & ENABLING ──
[UTILITIES] Mains Water Connection | P3U | Early — needed for site welfare | bar: M10 to M13
[UTILITIES] Borehole & Pump | P3U | Farm water supply | bar: M10 to M12
[UTILITIES] Septic Treatment Plant | P3U | Excavation with groundworks | bar: M10 to M12
[UTILITIES] Site Drainage & Swales | P3U | Parallel to groundworks | bar: M10 to M14
[UTILITIES] Grid Connection Install | P3U | After DNO approval ~M12 | bar: M12 to M15
[UTILITIES] Site Security (CCTV/gates) | P3U | Late — perimeter established | bar: M28 to M31
── MAIN HOUSE (sequential internally) ──
[MAIN HOUSE] Substructure | P3H | Strip/raft + basement dig | bar: M11 to M15
[MAIN HOUSE] Superstructure Walls | P3H | Overlaps substructure tail | bar: M14 to M19
[MAIN HOUSE] Roof Structure | P3H | bar: M18 to M22
[MAIN HOUSE] External Envelope | P3H | Slate/stone — long on-site | bar: M20 to M25
[MAIN HOUSE] First Fix MEP | P3H | Runs with envelope | bar: M22 to M26
[MAIN HOUSE] Internal Walls & Partitions | P3H | bar: M23 to M26
[MAIN HOUSE] Plaster & Insulation | P3H | bar: M25 to M28
[MAIN HOUSE] Second Fix MEP | P3H | bar: M27 to M30
[MAIN HOUSE] Finishes & Decoration | P3H | bar: M29 to M32
[MAIN HOUSE] Kitchen & Utility Fitout | P3H | Long lead items arrive | bar: M30 to M33
[MAIN HOUSE] Basement Fitout | P3H | Wine cellar, bar, AV | bar: M28 to M33
[MAIN HOUSE] Orangery & Outdoor Kitchen | P3H | Structure arrives from Ph2 | bar: M27 to M31
── ANNEXES (~3 months behind house) ──
[ANNEXES x2] Structure & Roof | P3A | Parallel to main house structure | bar: M14 to M21
[ANNEXES x2] Envelope & Fitout | P3A | bar: M20 to M28
[ANNEXES x2] MEP & Finishes | P3A | bar: M26 to M31
── GARAGE & BARNS (parallel from M12) ──
[GARAGE] Structure, Roof & Fitout | P3G | Simple structure — fast build | bar: M12 to M20
[BARNS] Foundations & Steel Frame | P3G | Steel portal frame 14-18wk lead | bar: M12 to M18
[BARNS] Cladding, MEP & Fitout | P3G | bar: M17 to M23
── GYM & WELLNESS ──
[GYM] Structure & Shell | P3W | Parallel to annexes | bar: M14 to M19
[GYM] Fitout (sauna/pool/cold plunge) | P3W | Equipment lead times 3-4 months | bar: M25 to M32
── ENERGY SYSTEMS ──
[ENERGY] Wind Turbine | P3E | Planning + groundworks | bar: M20 to M24
[ENERGY] Solar PV Installation | P3E | After roof complete | bar: M24 to M27
[ENERGY] Battery Storage | P3E | bar: M26 to M28
[ENERGY] Water Collection System | P3E | bar: M25 to M28
── FARM INFRASTRUCTURE (independent) ──
[FARM] Fencing & Gates | P3F | Largely independent stream | bar: M15 to M22
[FARM] Irrigation & Water Troughs | P3F | After borehole complete | bar: M18 to M23
[FARM] Animal Housing & Coops | P3F | bar: M20 to M26
[FARM] Greenhouse & Poly Tunnel | P3F | Structure from Ph2 | bar: M18 to M24
[FARM] Veg Beds, Fruit Trees, Orchard | P3F | bar: M24 to M29
[FARM] Farm Equipment (delivery) | P3F | bar: M30 to M32
── LANDSCAPING (tail — protect from traffic) ──
[LANDSCAPE] Wild Pond | P3L | Excavation early, planting late | bar: M20 to M24
[LANDSCAPE] Driveway & External Paving | P3L | After main construction traffic done | bar: M22 to M27
[LANDSCAPE] Garden Landscaping | P3L | Late — protect from construction | bar: M27 to M33
[LANDSCAPE] Outdoor Furniture & Lighting | P3L | bar: M31 to M33
Phase 4: Testing, Acceptance & Certification | PHASE | Overlaps Phase 3 tail | bar: M31 to M36
MEP & Utilities Commissioning | P4 | Systems commissioned as complete | bar: M31 to M34
Building Control Inspections | P4 | bar: M32 to M35
Snagging & Handover | P4 | bar: M34 to M36
Phase 5: In-Service Operations | PHASE | Commences at handover → ongoing | bar: M36
LEGEND
Phase 1: Planning (M1–6)
Phase 2: Design & Procurement (M3–12) — overlaps Ph1
Phase 3: Build (M10–33) — 6 parallel streams at peak
Utilities & Enabling Works (first on site M10)
Main House (sequential internally, M11–33)
Annexes x2 (~3 months behind house, M14–31)
Garage & Barns (fully parallel from M12)
Gym & Wellness (parallel structure M14, fitout M25+)
Energy Systems (solar after roof M24, wind M20)
Farm Infrastructure (independent stream M15+)
Landscaping (deliberately late M22+, protect from traffic)
Phase 4: Testing & Commissioning (M31–36, overlaps Ph3 tail)
KEY PROGRAMME ASSUMPTIONS:
• Total programme ~36 months from PM appointment to handover
• Phases overlap — Phase 2 starts M3 (not after Phase 1 closes); Phase 3 starts M10 with long-lead procurement from M6
• Phase 3 peak concurrent activity: months 18–26 — main house envelope, annexes, garage/barns, gym shell, farm infra all running simultaneously
• Main house build is internally sequential (foundations → structure → envelope → services → fit-out) but runs in parallel with all other structures
• Landscaping and external finishes deliberately scheduled late (M22+) to protect from construction traffic damage
• Critical path: Main house substructure (M11) → superstructure → roof → envelope → second fix → finishes → handover (M36)
• North Devon risk: weather delays est. +2–4 weeks; material delivery delays +2–6 weeks (factored into High duration scenario)
• DNO grid connection is a programme risk — rural Devon connections can take 6–12 months; application raised in Phase 2 (M3)